## SI Quotation Guide
LG CNS Standard Quotation
Hướng dẫn cách điền file Estimation
Effort Estimation | Bảng tính effort của từng tính năng nhỏ, theo loại hình dev (UI/BE/Batch...), loại tính năng (CRUD), độ khó (C1~C5), phân loại phát triển mới/update, Tỷ lệ phải sửa khi tái sử dụng (tỷ lệ càng thấp càng đỡ tốn effort), Effort khác | ① Dev Effor base on Effort tabl
Bảng tiêu chuẩn_ Định nghĩa Loại hình Dev | Phân loại theo từng loại hình Dev và phát triển mới/ sửa đổi, độ phức tạp, Effort phát triển của từng loại | Sheet Details Effort
Loại tính năng | Chia làm 4 loại CRUD
Độ khó | Tiêu chuẩn để xác định độ khó theo từng loại hình Dev | Sheet Difficulty (Complexity)
Phân loại | - Phát triển mới: Phát triển mới hoàn toàn (Create) - Phát triển update: ví dụ với loại tính năng Delete - Phát triển mới bằng tái sử dụng: Ví dụ với loại tính năng Edit, View
Tỷ lệ thay đổi khi tái sử dụng | Phải sửa < 33% khi tái sử dụng Phải sửa từ 33~65% khi tái sử dụng Phải sửa trên 66% khi tái sử dụng
Effort khác
Refer to the Standard Quotation (Family SI) Guide
Quotation method
Step1.Define the unit process - (1)Public check-based development man-hours sheet
Step2.Calculation of development man-hours - (1)Public check-based development man-hours sheet
Step3.Calculation of man-hours outside of development - (2)Development External Aviation Sheet
essential
essential
essential
essential
*Decision criteria: Unless it is difficult to determine the scope of pre-development and the MM estimate is reasonable, the basic principle is to estimate based on standard blank checks.
*Requirements, separated and created into independent unit processes (EP: Elementary Process, Bonn) centered on the main functions (input, modification, deletion, inquiry) ※ Standard of Software Business Price - Ministry of Information and Communication Notice No. 2003-14 (2003. 2. 10> : The bone is the smallest unit of a program that can independently execute functions of each type such as input, inquiry, modification, output, etc., and it refers to a set unit of steps designed with a low degree of coupling between the bones and a high degree of cohesion between the internal steps of the bone.
1. Inputs of development/processing/function type, new/change, difficulty (complexity) by unit process (H~M columns) 2. 'New Reuse': When developing a new function by referring to an existing source, the man-hours for applying reuse are automatically calculated by the 'Reuse Change Rate' selection value for each unit process and the 'Reuse Difficulty' in the project basic information sheet. * Reuse change rate: The percentage of changes in the original source and the newly generated code in the total 4. Only when the development type is selected as 'Other', other man-hours are required: Reflections of development-related activities or additional man-hours that are not included in the standard blank cheque (e.g., regression, integrated exam, conversion data extraction/verification, learning curve, package configuration, development environment setup, etc.) 5. In 'Difficulty, Reuse, and Other Man-Hours Application Details', if necessary, enter the basis for determining the degree of difficulty and the impact of reuse.
1. In addition to the head count directly input into the development process, the manpower required to perform additional roles such as management is calculated based on MM. 2. Calculate the total man-hours of the standard estimate by combining the development man-hours and the management and non-development man-hours and check the results.
Enter project information -Basic project information sheet
essential
Step4.Preparation of Detailed Head Count Input Plan - Reference)Detailed Head Count Input Plan sheet
1. Establish a monthly input plan for each expected head count based on total man-hours (considering the work pre-and post-work relationship, minimum input period, possible time of input/withdrawal, additional expected work, etc.) 2. Basically, the standard unit price corresponding to the standard level is applied, and if it is determined as a specific unit price, the corresponding unit price is entered. 3. Confirm the final project size and amount
Step5.Review the Quotation Results
Step6. Submission of quotation and proposal (CP preparation)
Exceptionally, if a discount is applied to the contract amount, the difference from the quoted amount is indicated as the discount amount in the quotation (specify the reason for the discount, such as a discount reflecting the special situation of each customer determined as other) * Only with the approval of the person in charge
Quotation based on standard blank cheque
MM-based estimation and input plan preparation - (3)MM-based quotation sheet
essential
MM-based quotation
MM-based quotation is exceptionally applied when it is difficult to determine the scope of pre-development and the MM estimate is reasonable. - PI/Consulting, Equipment/Facility Setup (in case of work not listed in the standard cheque), Dispatch of manpower to the customer, After opening, customer support, additional/residual development, solution purchase/setup, etc. - Roll-in/out application and support activities (e.g. user training, setup, business trip support, etc.) - When the overall scope/scale is not determined due to separate orders for each process (e.g. Analysis/Design Only)
* WIRE Competency-based Price System: Standard Quotation (Family SI) - https://wire.lgcns.com/confluence/x/gAJ8Cw

## Dev breaking tasks (2) (hidden)
Level 1 | Level 2 | Level 3 | Function
#REF! | #REF! | #REF! | #REF! | Dự kiến không làm trong phase 1
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF!
User and permission | User management | #DIV/0!

## Basic Project Information
About the project | Project Code/Name | CVM | Establishment of OOOO system
| Business | LG Electronics |  | Premium Pricing Eligibility | ERP(SAP) : 1.20
| Estimator (Affiliation/Name) | Hong Quotation (OOO Team in charge of DTO Division)
| Quotation method | Quotation based on standard blank cheque
| About Existing Systems (Only if there is reuse) | Reusable |  | Reusable
|  | Degree of program modularity and clarification of functions |  | Super Easy:10
|  | Degree of documentation and source code description |  | Normal:30
|  | Reuse difficulty |  | 1.16
※ Please select whether or not you want to be "Premium Pricing" for your project. (Smart Factory, ERP (SAP), Big Data Business, etc.)
Quotation Results | category | Development Man-Month - Standard Man-month (mm) | Out-of-development man-hours (mm) | Total (MM, thousand KRW)
(a) Blank check/MM-based quotation man-hours
(b) Blank check/MM-based estimate amount
(c) Actual Input Plan
Variance(MM) : (c) - (a)
* Variance means that if it is +, it means that the actual input is greater [Actual input plan - (blank cheque based or MM based quotation)]
----------------------------------------------------------- Below Reference -----------------------------------------------------------
※ Note: Reuse difficulty level evaluation criteria |  |  |  |  | (Software Business Cost Calculation Guide, 2021. KOSA)
category | Very difficult | difficulty | usually | Easy | Super easy
Cooldown difficulty | 50 | 40 | 30 | 20 | 10
(1) Degree of program modularity and clarification of functions | Program Modularization - None, Correspondence of Modules and Functions - None | Program modularity - insufficient, degree of correspondence between modules and functions - low | Program Modularity - Moderate, Degree of correspondence between modules and functions - Moderate | Program Modularity - Excellent, Degree of Module and Function Correspondence - High | Program modularity - very good, correspondence of modules and functions - very high
(2) Degree of documentation and description of source code | Requirements Statement, Design Document, System Manual, User Documentation of manuals and description of source code annotations are not available | Requirements Statement, Design Document, System Manual, User Among the documentation such as documentation and description of source code comments, one is moderate and the other is not. | Requirements Statement, Design Document, System Manual, User Documentation of manuals and descriptions of source code comments are both moderate | Requirements Statement, Design Document, System Manual, User Documentation of manuals, etc., and description of source code annotations are either well done. | Requirements Statement, Design Document, System Manual, User Documentation of manuals and description of source code comments are all well done.

## ① Dev Effort table
Step1. Defining Unit Processes | [8 empty] | Step2. Development man-hours calculation | [10 empty] | Custom Fields (Reference)
No | LEVEL1 Task/System Name | LEVEL2 Main job name | LEVEL3 Screen or detailed job name | LEVEL4 Unit Process | Detailed Implementation of Unit Process Explanation | Actual hours | Priority | Development Type | disposal type | function type | Difficulty | New/Change category | reuse Rate of change | Standard Man-hours | reuse Applied man-hours | Other | Final Airlift (MH) | Difficulty, reuse, and other man-hours application details | Remarks | Customization Field 1 | Customization Field 2 | Customization Field 3 | Customization Field 4 | Customization Field 5
[14 empty] | 1227.91 | 1200.8545 | 0 | 1200.8545
1 | Analyzing requirements | Analyzing requirements | user management analyzing | Analyze requirements for the User list |  | 5 | 1 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
|  |  |  | Analyze requirements User CRUD modal |  | 3.1 |  | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
|  |  | Group User management analyzing | Analyze requirements for the Group User list |  | 5 |  | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
|  |  |  | Analyze requirements for the Group User CRUD modal |  | 5 |  | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
|  |  | Role management analyzing | Analyze requirements for the Role list |  | 9.1 |  | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
|  |  |  | Analyze requirements Role CRUD modal |  | 9.1 |  | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
|  |  | CV management analyzing | Analyze requirements for the CV list screen |  | 9.1 |  | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
|  |  |  | Analyze requirements for the CV detail screen |  | 5 |  | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
|  |  |  | Analyze requirements for the Upload CV screen |  | 5 |  | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
|  |  | Rule management analyzing | Analyze requirements for the rule list screen (to setup rule for filtering CV from 3rd party) |  | 3.1 |  | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
|  |  | Interviewing analyzing | Analyze requirements for the Scheduled Interview list screen |  | 9.1 |  | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
|  |  |  | Analyze requirements for the a popover for scheduling interview |  | 5 |  | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
|  |  |  | Analyze requirements for the My calendar screen |  | 9.1 |  | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
|  |  |  | Analyze requirements for the Evaluating candidates screen |  | 5 |  | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
|  |  |  | Analyze requirements for the Evaluating detail screen |  | 9.1 |  | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
|  |  | Onboarding analyzing | Analyze requirements for the onboarding list screen |  | 9.1 |  | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
|  |  |  | Analyze requirements for the scheduling onboarding screen |  | 5 |  | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
|  |  | Subscription analyzing | Analyze requirements for the Job position list screen |  | 9.1 |  | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
|  |  |  | Analyze requirements for the job - detail screen |  | 5 |  | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
|  |  |  | Analyze requirements for the a job subscription screen |  | 3.1 |  | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
|  |  | Dashboard analyzing | Analyze requirements for the a bell ringing put at every page |  | 9.1 |  | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
|  |  |  | Analyze requirements for the Homepage - dashboard |  | 3.1 |  | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
2 | Designing | Designing Database | Designing Database | BE: Designing Database |  | 14.1 | 1 | Online_C/S |  |  | C5 | New |  | 23.97 | 23.97 |  | 23.97
3 |  | Designing wireframe | user management wireframe | Designing wireframe for the User list |  | 5 | 1 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
3 |  |  |  | Designing wireframe User CRUD modal |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
|  |  | Group User management wireframe | Designing wireframe for the Group User list |  | 5 | 1 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
|  |  |  | Designing wireframe for the Group User CRUD modal |  | 5 | 1 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
4 |  |  | Role management wireframe | Designing wireframe for the Role list |  | 9.1 | 2 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
|  |  |  | Designing wireframe Role CRUD modal |  | 9.1 | 1 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
5 |  |  | CV management wireframe | Designing wireframe for the CV list screen |  | 14.1 | 1 | Online_C/S |  |  | C5 | New |  | 23.97 | 23.97 |  | 23.97
6 |  |  |  | Designing wireframe for the CV detail screen |  | 9.1 | 1 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
7 |  |  |  | Designing wireframe for the Upload CV screen |  | 5 | 2 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
|  |  | Rule management wireframe | Designing wireframe for the rule list screen (to setup rule for filtering CV from 3rd party) |  | 3.1 | 2 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
8 |  |  | Interviewing wireframe | Designing wireframe for the Scheduled Interview list screen |  | 9.1 | 1 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
9 |  |  |  | Designing wireframe for the a popover for scheduling interview |  | 5 | 1 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
10 |  |  |  | Designing wireframe for the My calendar screen |  | 9.1 | 1 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
11 |  |  |  | Designing wireframe for the Evaluating candidates screen |  | 5 | 1 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
12 |  |  |  | Designing wireframe for the Evaluating detail screen |  | 9.1 | 1 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
13 |  |  | Onboarding wireframe | Designing wireframe for the onboarding list screen |  | 9.1 | 2 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
14 |  |  |  | Designing wireframe for the scheduling onboarding screen |  | 5 | 2 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
16 |  |  | Subscription wireframe | Designing wireframe for the Job position list screen |  | 9.1 | 1 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
17 |  |  |  | Designing wireframe for the job - detail screen |  | 5 | 1 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
18 |  |  |  | Designing wireframe for the a job subscription screen |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
|  |  | Dashboard wireframe | Designing wireframe for the a bell ringing put at every page |  | 9.1 | 1 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
21 |  |  |  | Designing wireframe for the Homepage - dashboard |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
22 | Creating project base | Building DB tables | Building DB tables | Building DB tables |  | 1.8 | 1 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
23 |  | Building BE project | Building BE project | Building BE project |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
24 |  | Building FE project | Building FE base structure | Building FE project |  | 11.9 | 1 | Online_Web |  |  | C5 | New |  | 20.23 | 20.23 |  | 20.23
24 |  |  | Building FE common components | common table components |  | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
24 |  |  |  | Common drawer components | including slot title, content, footer action | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
24 |  |  |  | Common dialog confirm, modal |  | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
24 |  |  |  | Building calendar |  | 7.4 | 1 | Online_Web |  |  | C4 | New |  | 12.58 | 12.58 |  | 12.58
25 | User and permission | User management | User list and asigning role screen | BE: api get User and their role by condition, paginable |  | 3.1 | 1 | Online_C/S |  |  | C2 | New | 66%이상 - 0.75 | 5.27 | 5.27 |  | 5.27
26 |  |  |  | BE: api CUD User and assign roles for them |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
27 |  |  |  | FE: User with their role list page screen |  | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
28 |  |  |  | FE: a popup to create and update user and their role |  | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
29 |  | Role management | Role management screen | BE: api get permission list |  | 1.8 | 2 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
30 |  |  |  | BE: api CUD permission |  | 1.8 | 2 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
31 |  |  |  | BE: api get role list |  | 3.1 | 2 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
32 |  |  |  | BE: api CUD role |  | 3.1 | 2 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
33 |  |  |  | FE: a screen to list permission |  | 5 | 2 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
34 |  |  |  | FE: a popup to create |  | 5 | 2 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
34 |  |  |  | FE: a popup update permission |  | 4.35 | 2 | Online_Web |  |  | C3 | New Reuse | 66%이상 - 0.75 | 8.5 | 7.395 |  | 7.395
35 |  |  |  | FE: a screen to list role |  | 5 | 2 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
36 |  |  |  | FE: a popup to create role |  | 5 | 2 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
36 |  |  |  | FE: a popup to update role |  | 2.9 | 2 | Online_Web |  |  | C3 | New Reuse | 33%-66% - 0.5 | 8.5 | 4.93 |  | 4.93
37 | CV | CV management | CV list screen | BE: Api get CV list by condition, paginable |  | 5 | 1 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
39 |  |  |  | Be: api export excel |  | 9.1 | 1 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
40 |  |  |  | Fe: CV list screen |  | 11.9 | 1 | Online_Web |  |  | C5 | New |  | 20.23 | 20.23 |  | 20.23
40 |  |  |  | Fe: filter cv area |  | 11.9 | 1 | Online_Web |  |  | C5 | New |  | 20.23 | 20.23 |  | 20.23
41 |  |  |  | Fe: export excel button |  | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
42 |  |  | CV detail screen | Be: api get CV detail |  | 5 | 1 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
43 |  |  |  | BE: api update CV |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
44 |  |  |  | BE: api update CV status |  | 1.8 | 1 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
45 |  |  |  | BE: api suggestion |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
46 |  |  |  | FE: area view CV file |  | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
47 |  |  |  | FE: Approve or Reject function |  | 3.2 | 1 | Online_Web |  |  | C2 | New |  | 5.44 | 5.44 |  | 5.44
48 |  |  |  | FE: detail information |  | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
49 |  |  |  | FE: suggestion function |  | 3.2 | 1 | Online_Web |  |  | C2 | New |  | 5.44 | 5.44 |  | 5.44
50 |  |  | Upload CV screen | BE: api upload file |  | 1.8 | 2 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
51 |  |  |  | BE: api create CV information |  | 1.8 | 2 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
52 |  |  |  | FE: upload CV screen |  | 3.2 | 2 | Online_Web |  |  | C2 | New |  | 5.44 | 5.44 |  | 5.44
53 | Scheduling | Interview scheduling | Scheduled Interview list screen | BE: api get scheduled inteview list |  | 5 | 1 | Online_C/S |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
54 |  |  |  | BE: api get scheduled interview detail |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
55 |  |  |  | BE: api send email for interviewers |  | 1.8 | 1 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
56 |  |  |  | FE: list scheduled inteview by day, on a calendar |  | 11.9 | 1 | Online_Web |  |  | C5 | New |  | 20.23 | 20.23 |  | 20.23
57 |  |  |  | FE: view scheduled interview detail on a pop over |  | 7.4 | 1 | Online_Web |  |  | C4 | New |  | 12.58 | 12.58 |  | 12.58
58 |  |  | a popover for scheduling interview | BE: api for scheduling an interview |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
59 |  |  |  | FE: a pop over for scheduling interview |  | 0 | 1 | [6 empty] | 0 | 0 |  | 0
60 | Evaluating candidates while interviewing | Evaluating candidates while interviewing | scheduled interview list screen (see the below My calendar screen) | BE: api to get scheduled interview by interviewer's ID (user Id) or CV's ID |  | 0.899 | 1 | Online_C/S |  |  | C2 | New Reuse | 33%미만 - 0.25 | 5.27 | 1.5283 |  | 1.5283
61 |  |  |  | FE: build the My calendar screen, | this screen will show scheduled interview list, when users click at cells will open a popup to read CV, scheduled interview and evaluating candidates (see the below Evaluating candidates screen) | 6.438 | 1 | Online_Web |  |  | C4 | New Reuse | 66%이상 - 0.75 | 12.58 | 10.9446 |  | 10.9446
62 |  |  | Evaluating candidates screen | BE: api evaluate candidates |  | 1.8 | 1 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
63 |  |  |  | FE: a form for evaluating candidates |  | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
64 |  |  | Evaluating detail screen | BE: api get Evaluating detail |  | 1.8 | 1 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
65 |  |  |  | BE: api export pdf |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
66 |  |  |  | FE: Evaluating detail screen |  | 3.2 | 1 | Online_Web |  |  | C2 | New |  | 5.44 | 5.44 |  | 5.44
67 | Onboarding | Scheduling onboarding | onboarding list screen | BE: api get onboarding list |  | 3.1 | 2 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
68 |  |  |  | FE: list onboarding info by day, on a calendar |  | 6.438 | 2 | Online_Web |  |  | C4 | New Reuse | 66%이상 - 0.75 | 12.58 | 10.9446 |  | 10.9446
69 |  |  |  | FE: view onboarding detail on a pop over |  | 4.35 | 2 | Online_Web |  |  | C3 | New Reuse | 66%이상 - 0.75 | 8.5 | 7.395 |  | 7.395
70 |  |  | scheduling onboarding screen | BE: api scheduling onboarding |  | 3.1 | 2 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
71 |  |  |  | FE: a pop over for scheduling onboarding |  | 2.9 | 2 | Online_Web |  |  | C3 | New Reuse | 33%-66% - 0.5 | 8.5 | 4.93 |  | 4.93
72 | Email and notification | Tính năng thông báo: mail, icon thông báo | a bell ringing put at every page | BE: api return notify list by user ID |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
|  |  |  | BE: api return number of new notify |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
73 |  |  |  | BE: an utill class to send email |  | 1.8 | 2 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
74 |  |  |  | BE: api update notify by user ID |  | 1.8 | 1 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
75 |  |  |  | FE: code a bell for nitification |  | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
76 |  |  |  | FE: popup for showing notification list. | When there are many notification, will merge them into one notification. - 4 kinds of notification: +) scheduled interview -> redirect to my calendar +) onboarding -> redirect to my calendar +) suitable CV -> redirect to CV list +) suggestion -> redirect to CV list | 11.9 | 1 | Online_Web |  |  | C5 | New |  | 20.23 | 20.23 |  | 20.23
77 |  | My calendar screen | My calendar screen | BE: api to get scheduled interview by interviewer's ID (user Id) and other information that need to use calendar |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
78 |  |  |  | FE: build a my calendar screen |  | 0 | 1 | [6 empty] | 0 | 0 |  | 0
79 | Job | Job position management | Job position list screen | BE: api get job position list |  | 1.8 | 2 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
80 |  |  |  | BE: api get criteria and weight (trọng số) |  | 3.1 | 2 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
81 |  |  |  | BE: api CUD job position |  | 1.8 | 2 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
82 |  |  |  | BE: api CUD criteria and weight |  | 3.1 | 2 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
83 |  |  |  | FE: a job position with criteria and weight screen |  | 5 | 2 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
84 |  |  |  | FE: a popup to CUD job and criteria with weight |  | 7.4 | 2 | Online_Web |  |  | C4 | New |  | 12.58 | 12.58 |  | 12.58
85 | Subscription | Subscribe a specific job | A job - requirement list screen | BE: api get job, criteria and weight list |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
86 |  |  |  | FE: A job - criteria list screen |  | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
88 |  |  |  | BE: api job subscription list by UserID |  | 1.8 | 1 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
89 |  |  |  | FE: a job subscription screen |  | 5 | 1 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
90 |  | Suitable CV scanning job | Suitable CV scanning job (schedule, batch job) | BE: Create a job to evaluate score of CV and then send notification to subscribers |  | 9.1 | 1 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
91 | Fetch CV from 3rd parties | Fetch CV by rule, extract main information | A job to fetch CV by rule, extract main information | A job to fetch CV by rule, extract main information |  | 9.1 | 1 | Online_C/S |  |  | C4 | New |  | 15.47 | 15.47 |  | 15.47
92 |  |  | rule list screen | BE:api get rule list |  | 1.8 | 2 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
93 |  |  |  | BE: api update rule |  | 1.8 | 2 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
94 |  |  |  | FE: rule list screen |  | 5 | 2 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
95 |  |  |  | FE: a popup create update rule |  | 5 | 2 | Online_Web |  |  | C3 | New |  | 8.5 | 8.5 |  | 8.5
95 |  |  |  | FE: a popup update rule |  | 2.9 | 2 | Online_Web |  |  | C3 | New Reuse | 33%-66% - 0.5 | 8.5 | 4.93 |  | 4.93
96 | Log | Log |  | BE: class util log: create a log by: function, userID, CV ID, action, date time, content |  | 1.8 | 2 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
97 | Statistic | Tính năng phân tích thông kê | Biểu đồ tròn ti lệ % status trên tổng số CV đã applied | BE: api get number of status and total CV |  | 1.8 | 1 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
98 |  |  |  | FE: Vẽ biểu đồ tròn ti lệ % status trên tổng số CV đã applied |  | 7.4 | 1 | Online_Web |  |  | C4 | New |  | 12.58 | 12.58 |  | 12.58
99 |  |  | Biểu đồ cột các trạng thái CV theo ngày, tuần, tháng (start date, end date) | BE: api get number of status by time |  | 3.1 | 1 | Online_C/S |  |  | C2 | New |  | 5.27 | 5.27 |  | 5.27
100 |  |  |  | FE: Vẽ biểu đồ cột các trạng thái CV theo ngày, tuần, tháng (start date, end date) |  | 6.438 | 1 | Online_Web |  |  | C4 | New Reuse | 66%이상 - 0.75 | 12.58 | 10.9446 |  | 10.9446
101 |  |  | Biểu đồ cột số lượng các CV từ các nguồn khác nhau theo ngày, tuần, tháng (start date, end date) | BE: api get number of CV from different sources by time |  | 0.522 | 1 | Online_C/S |  |  | C1 | New Reuse | 33%미만 - 0.25 | 3.06 | 0.8874 |  | 0.8874
102 |  |  |  | FE: vẽ biểu đồ cột số lượng các CV từ các nguồn khác nhau theo ngày, tuần, tháng (start date, end date) |  | 4.35 | 1 | Online_Web |  |  | C3 | New Reuse | 66%이상 - 0.75 | 8.5 | 7.395 |  | 7.395
103 |  |  | Biểu đồ cột các job applied theo ngày, tuần, tháng (start date, end date) | BE: api get number of applied jobs by time |  | 1.8 | 1 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
104 |  |  |  | FE: vẽ biểu đồ cột các job applied theo ngày, tuần, tháng (start date, end date) |  | 4.35 | 1 | Online_Web |  |  | C3 | New Reuse | 66%이상 - 0.75 | 8.5 | 7.395 |  | 7.395
105 |  |  | Biểu đồ cột các skills CV theo ngày, tuần, tháng (start date, end date) | BE: api get number of skills by time |  | 1.8 | 1 | Online_C/S |  |  | C1 | New |  | 3.06 | 3.06 |  | 3.06
106 |  |  |  | FE: Vẽ biểu đồ cột các skills CV theo ngày, tuần, tháng (start date, end date) |  | 4.35 | 1 | Online_Web |  |  | C3 | New Reuse | 66%이상 - 0.75 | 8.5 | 7.395 |  | 7.395
107 | dashboard | dashboard | dashboard | dashboard |  | 0 | 1 | [6 empty] | 0 | 0 |  | 0
81 | Login page |  |  |  |  | 7.4 |  | Online_Web |  |  | C4 | New |  | 12.58 | 12.58 |  | 12.58
82 | Layout |  |  |  |  | 11.9 |  | Online_Web |  |  | C5 | New |  | 20.23 | 20.23 |  | 20.23
83 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
84 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
85 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
86 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
87 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
88 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
89 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
90 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
91 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
92 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
93 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
94 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
95 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
96 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
97 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
98 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
99 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
100 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
101 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
102 | [5 empty] | 0 | [7 empty] | 0 | 0 |  | 0
103 | [13 empty] | 0 | 0 |  | 0
104 | [13 empty] | 0 | 0 |  | 0
105 | [13 empty] | 0 | 0 |  | 0
105 | [13 empty] | 0 | 0 |  | 0
106 | [13 empty] | 0 | 0 |  | 0
107 | [13 empty] | 0 | 0 |  | 0
108 | [13 empty] | 0 | 0 |  | 0
109 | [13 empty] | 0 | 0 |  | 0
110 | [13 empty] | 0 | 0 |  | 0
111 | [13 empty] | 0 | 0 |  | 0
112 | [13 empty] | 0 | 0 |  | 0
113 | [13 empty] | 0 | 0 |  | 0
114 | [13 empty] | 0 | 0 |  | 0
115 | [13 empty] | 0 | 0 |  | 0
116 | [13 empty] | 0 | 0 |  | 0
117 | [13 empty] | 0 | 0 |  | 0
118 | [13 empty] | 0 | 0 |  | 0
119 | [13 empty] | 0 | 0 |  | 0
120 | [13 empty] | 0 | 0 |  | 0
121 | [13 empty] | 0 | 0 |  | 0
122 | [13 empty] | 0 | 0 |  | 0
123 | [13 empty] | 0 | 0 |  | 0
124 | [13 empty] | 0 | 0 |  | 0
125 | [13 empty] | 0 | 0 |  | 0
126 | [13 empty] | 0 | 0 |  | 0
127 | [13 empty] | 0 | 0 |  | 0
128 | [13 empty] | 0 | 0 |  | 0
129 | [13 empty] | 0 | 0 |  | 0
130 | [13 empty] | 0 | 0 |  | 0
131 | [13 empty] | 0 | 0 |  | 0
132 | [13 empty] | 0 | 0 |  | 0
133 | [13 empty] | 0 | 0 |  | 0
134 | [13 empty] | 0 | 0 |  | 0
135 | [13 empty] | 0 | 0 |  | 0
136 | [13 empty] | 0 | 0 |  | 0
137 | [13 empty] | 0 | 0 |  | 0
138 | [13 empty] | 0 | 0 |  | 0
139 | [13 empty] | 0 | 0 |  | 0
140 | [13 empty] | 0 | 0 |  | 0
141 | [13 empty] | 0 | 0 |  | 0
142 | [13 empty] | 0 | 0 |  | 0
143 | [13 empty] | 0 | 0 |  | 0
144 | [13 empty] | 0 | 0 |  | 0
145 | [13 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on O2: <신규/변경/재사용> 항목이 '신규 재사용'인 경우만 선택함
Note on R2: If the <Development Type> item is 'Other', enter other labor costs.

## 참고 (hidden)
구분 | 역량레벨 | 유효값 | 생산성 | LCP단가(24년) | LCP단가(23년) | ※ M/D, M/M 변환 기준 (1MM →) | 21
LG CNSL-0.5 | L-0.5 | 142.9 | 70% | 14652 | 13479
LG CNSL-1.0 | L-1.0 | 125 | 80% | 16744 | 15404
LG CNSL-1.5 | L-1.5 | 111.1 | 90% | 18838 | 17330
LG CNSL-2.0 | L-2.0 | 100 | 100% | 20930 | 19255
LG CNSL-2.5 | L-2.5 | 90.9 | 110% | 23024 | 21181
LG CNSL-3.0 | L-3.0 | 80 | 125% | 26164 | 24070
LG CNSL-3.5 | L-3.5 | 74.1 | 135% | 28255 | 25994
LG CNSL-4.0 | L-4.0 | 66.7 | 150% | 31396 | 28883
LG CNSL-4.5 | L-4.5 | 60.6 | 165% | 34535 | 31771
LG CNSL-5.0 | L-5.0 | 55.6 | 180% | 협상단가 | 협상단가
※ IT 신기술 대상 영역 할증 적용 (Premium Pricing) - 인공지능, 빅데이터 영역 : ‘IT서비스 기술역량 레벨 대가’에 1.3배 할증 적용 - 클라우드 컨설팅/이행, 아키텍처 컨설팅/이행, ERP(SAP)영역 : ‘IT서비스 기술역량 레벨 대가’에 1.2배 할증 적용 - 스마트팩토리 영역 : ‘IT서비스 기술역량 레벨 대가’에 1.05배 할증 적용(단, R&D영역 할증 제외) [2024년 변경사항]

## Dev breaking tasks
Level 1 | Level 2 | Level 3 |  | Level 3 | Level 4 | Detail function | Description
User and permission | User management | 1 | Danh sách users CRUD | User list and asigning role screen | BE: api get User and their role by condition, paginable
BE: api CUD User and assign roles for them
FE: User with their role list page screen
FE: a popup to create and update user and their role
| Role management |  |  | Role management screen | BE: api get permission list
BE: api CUD permission
BE: api get role list
|  | 3 | Quản lý danh sách team |  | BE: api CUD role
|  | 1 | quản lý danh sách quyền |  | FE: a screen to list permission
FE: a popup to create and update permission
FE: a screen to list role
FE: a popup to create and update role
CV | CV management |  |  | CV list screen | BE: Api get CV list by condition, paginable
Be: api export excel
Fe: CV list screen
Fe: export excel
|  |  |  | CV detail screen | Be: api get CV detail
BE: api update CV
BE: api update CV status
BE: api suggestion
FE: area view CV file
FE: Approve or Reject function
FE: detail information
FE: suggestion function
|  |  |  | Upload CV screen | BE: api upload file
BE: api create CV information
FE: upload CV screen
Scheduling | Interview scheduling | 3 | Calendar board để xếp lịch | Scheduled Interview list screen | BE: api get scheduled inteview list | có thể phỏng vấn nhiều vòng, nếu pass vòng 1 và fail vòng 2 thì team leader có thể cân nhắc tuyển ứng viên cho team khác. Đối với phỏng vấn vòng 2, người pv có thể là HQ.
BE: api get scheduled interview detail
BE: api send email for interviewers
FE: list scheduled inteview by day, on a calendar
FE: view scheduled interview detail on a pop over
|  |  |  | a popover for scheduling interview | BE: api for scheduling an interview
FE: a pop over for scheduling interview
Evaluating candidates while interviewing | Evaluating candidates while interviewing |  |  | scheduled interview list screen (see the below My calendar screen) | BE: api to get scheduled interview by interviewer's ID (user Id)
[5 empty] | FE: My calendar screen | this screen will show scheduled interview list, when users click at cells will open a popup to read CV, scheduled interview and evaluating candidates (see the below Evaluating candidates screen)
|  |  |  | Evaluating candidates screen | BE: api evaluate candidates
[5 empty] | FE: a form for evaluating candidates | show interviewing round number
|  |  |  | Evaluating detail screen | BE: api get Evaluating detail | show interviewing round results
BE: api export pdf
FE: Evaluating detail screen
Onboarding | Scheduling onboarding |  |  | onboarding list screen | BE: api get onboarding list
FE: list onboarding info by day, on a calendar
FE: view onboarding detail on a pop over
|  |  |  | scheduling onboarding screen | BE: api scheduling onboarding
FE: a pop over for scheduling onboarding
Email and notification | Tính năng thông báo: mail, icon thông báo | 4 | subcribers: nhận thông báo các CVs thỏa mãn yêu cầu | a bell ringing put at every page | BE: api return notify list by user ID | cài đặt nhận thông báo
BE: api update notify by user ID
FE: code a bell for nitification
FE: code a popup for showing notification list. When there are many notification, will merge them into one notification. - 4 kinds of notification: +) scheduled interview -> redirect to my calendar +) onboarding -> redirect to my calendar +) suitable CV -> redirect to CV list +) suggestion -> redirect to CV list
|  |  |  | My calendar screen | BE: api to get scheduled interview by interviewer's ID (user Id) and other information that need to use calendar
FE: build a my calendar screen
Job | Job position management |  |  | Job position list screen | BE: api get job position list
BE: api get criteria and weight (trọng số)
BE: api CUD job position
BE: api CUD criteria and weight
FE: a job position with criteria and weight screen
FE: a popup to CUD job and criteria with weight
Subscription | Subscribe a specific job | 3 | Trang cài đặt các tiêu chí (hỗ trơ nhiều nhóm tiêu chí) | job - criteria list screen | BE: api get job, criteria and weight list | cài đặt nhận thông báo
FE: A job - criteria list screen
|  |  |  | a job subscription screen | BE: api job subscription by UserID
BE: api job subscription list by UserID
FE: a job subscription screen
| Suitable CV scanning job |  |  | Suitable CV scanning job (schedule, batch job) | BE: Create a job to evaluate score of CV and then send notification to subscribers
Fetch CV from 3rd parties | Fetch CV by rule, extract main information |  |  | A job to fetch CV by rule, extract main information | A job to fetch CV by rule, extract main information | Tính năng fetch CV về system từ 3rd party theo rule: lần phỏng vấn gần nhất không quá từ 3-6 tháng, ko làm ở Fpt software, Fpt IS.
|  |  |  | rule list screen | BE:api get rule list
BE: api update rule
FE: rule list screen
FE: a popup create update rule
Log | Log |  |  | class Util log | BE: class util log: create a log by: function, userID, CV ID, action, date time, content
Statistic | Tính năng phân tích thông kê | 1 | BIểu đồ thống kê theo thời gian: total, accepted, interviewed, onboarded | Biểu đồ tròn ti lệ % status trên tổng số CV đã applied | BE: api get number of status and total CV
FE: Vẽ biểu đồ tròn ti lệ % status trên tổng số CV đã applied
|  |  |  | Biểu đồ cột các trạng thái CV theo ngày, tuần, tháng (start date, end date) | BE: api get number of status by time
FE: Vẽ biểu đồ cột các trạng thái CV theo ngày, tuần, tháng (start date, end date)
|  | 1 | Biểu đồ tỉ lệ tương quan theo time: vị trí tuyển dụng, skills, status/total | Biểu đồ cột số lượng các CV từ các nguồn khác nhau theo ngày, tuần, tháng (start date, end date) | BE: api get number of CV from different sources by time
FE: vẽ biểu đồ cột số lượng các CV từ các nguồn khác nhau theo ngày, tuần, tháng (start date, end date)
|  |  |  | Biểu đồ cột các job applied theo ngày, tuần, tháng (start date, end date) | BE: api get number of applied jobs by time
FE: vẽ biểu đồ cột các job applied theo ngày, tuần, tháng (start date, end date)
|  |  |  | Biểu đồ cột các skills CV theo ngày, tuần, tháng (start date, end date) | BE: api get number of skills by time
|  | 2 | Thống kể theo vùng miền, độ tuổi, giời tính, nguồn tuyển dụng |  | FE: Vẽ biểu đồ cột các skills CV theo ngày, tuần, tháng (start date, end date)
Home page - dashboard | Home page - dashboard | Home page - dashboard | Home page - dashboard | Home page - dashboard | Home page - dashboard
Analyze requirements | Analyze requirements |  |  | Analyze requirements | Analyze requirements
Designing | Designing | 2 | Export excel | Designing Database | BE: Designing Database
|  | 2 | Hiệu suất đóng góp tuyển dụng | Designing wireframe | Designing wireframe for the User list and asigning role screen
|  | 1 | Danh sách tông quan các CVs |  | Designing wireframe for the Role management screen
|  |  | Trang xem chi tiết CV và accept CV |  | Designing wireframe for the CV list screen
|  |  | Upload CV (refer person) |  | Designing wireframe for the CV detail screen
|  |  | Export dữ liệu |  | Designing wireframe for the Upload CV screen
|  |  | Hõ trợ filter theo interviewer, accepter |  | Designing wireframe for the Scheduled Interview list screen
Designing wireframe for the a popover for scheduling interview
|  | 1 | Trang chi tiết theo ngày |  | Designing wireframe for the My calendar screen
|  | 4 | Thông báo lịch qua mail cho interviewer |  | Designing wireframe for the Evaluating candidates screen
|  | 1 | Trang xem chi tiết CV và comment đánh giá theo các tiêu chí |  | Designing wireframe for the Evaluating detail screen
|  | 3 | Calendar board để xếp lịch |  | Designing wireframe for the onboarding list screen
|  | 1 | Trang chi tiết theo ngày |  | Designing wireframe for the scheduling onboarding screen
|  | 4 | Thông báo lịch qua mail cho người phụ trách |  | Designing wireframe for the a bell ringing put at every page
Designing wireframe for the Job position list screen
|  | 4 | Đinh kỳ gửi report file cho HR, Admin,.. |  | Designing wireframe for the job - criteria list screen
|  | 4 | Thông báo có CV accepted, passed intervewing -> HR |  | Designing wireframe for the a job subscription screen
Designing wireframe for the Suitable CV scanning job (schedule, batch job)
|  | 1 | Auto fetch new CV |  | Designing wireframe for the rule list screen
|  |  | Auto convert data to DB data |  | Designing wireframe for the Homepage - dashboard
Creating base | Building DB tables |  |  | Building DB tables | Building DB tables
| Building BE project |  |  | Building BE project | Building BE project
| Building FE project |  |  | Building FE project | Building FE project
|  | 2 | log accept, interview, onboarding, rejected, option: view by ?

## (2) Development and external co
■ Summary
category | MM | Amount (one thousand won)
(1) Development labor cost - standard man-hours and others | 2 | 49709.8
(2) Labor costs other than development | 2 | 63839.2
(3) HW/SW, etc. | 0 | 0
計 | 4 | 113549 | ▶ Non-editable areas
Step3. Management & Development Calculation
category | Classification of duties | Job Description and Role | Level of technical competence | PP Eligibility | Surcharge Rate | Unit | Man-Lift(mm) | amount | Remarks
sum | [6 empty] | 4 | 113549
(1) Development labor cost - standard man-hours and others | development | ABAP Development | Market Unit Price | None of the above | 1 | 직접입력하세요 | 0 | 0
(1) Development labor cost - standard man-hours and others | development | △△ Development | L-4.0 | None of the above | 1 | 31396 | 0 | 0
(1) Development labor cost - standard man-hours and others | development | yes Development | L-1.0 | None of the above | 1 | 16744 | 1 | 16744 | Apply market unit price
(1) Development labor cost - standard man-hours and others | development | ᄆᄆdevelopment | L-4.0 | Smart Factory | 1.05 | 32965.8 | 1 | 32965.8 | Smart Factory Business Surcharge Application
(2) Labor costs other than development | Analysis/Design | Analysis/Design | L-4.0 | ERP(SAP) | 1.2 | 37675.2 | 1 | 37675.2
(2) Labor costs other than development | PM | PM | L-3.0 | None of the above | 1 | 26164 | 1 | 26164
(2) Labor costs other than development | Infrastructure Installation | yes Installation | L-4.0 | None of the above | 1 | 31396 | 0 | 0
(2) Labor costs other than development | Infrastructure Installation | ᄆᄆinstallation | Market Unit Price | None of the above | 1 | 직접입력하세요 | 0 | 0
(2) Labor costs other than development | Penetration Testing | security | L-4.0 | None of the above | 1 | 31396 | 0 | 0
(2) Labor costs other than development | Vulnerability Inspection | security | L-4.0 | None of the above | 1 | 31396 | 0 | 0
(2) Labor costs other than development | UX Planning | UX Design | L-2.0 | None of the above | 1 | 20930 | 0 | 0
(2) Labor costs other than development | guitar | Perform other project work | L-2.0 | None of the above | 1 | 20930 | 0 | 0
(2) Labor costs other than development | PI | Analysis/Design | L-4.0 | None of the above | 1 | 31396 | 0 | 0
(2) Labor costs other than development | QA | QA | L-4.0 | None of the above | 1 | 31396 | 0 | 0
(2) Labor costs other than development | PerformanceExam | exam | L-3.0 | None of the above | 1 | 26164 | 0 | 0
(3) HW/SW, etc. | [6 empty] | 0 | 0 | If the HW/SW amount is included in the quotation, it will be listed
※ If the input manpower is eligible for "Premium Pricing", please select whether or not you are eligible or not.

## Quote_Sample
Sushin | : |  | LGOO Business Innovation OO Team OOO Responsibility
Thank you for your business with us, and we quote you as below.
Quotation | : | 1132142.1659 |  |  | Tianyuan (VAT excluded)
(Unit: thousands of won)
Job Description |  | entry |  |  |  | Level of technical competence | Quantity(mm) | Unit | Offer price | Remarks
00Management System 000 Spread |  | Development Area |  | Based on standard blank cheques | OO Development | L-2.0 | 1.2191 | 19255 | 23474.5957
|  |  |  | Special (market) unit price | ABAP Developer | Market Unit Price | 8 | 20872 | 166976
|  | Non-Development Areas |  | Detailed Challenge Analysis |  | L-4.0 | 10 | 37547.9 | 375479 | PP(1.3) surcharge
|  |  |  | Installation of infrastructure facilities |  | L-2.5 | 5 | 21181 | 105905
|  |  |  | Project Manager |  | L-4.0 | 12 | 28883 | 346596
|  |  |  | Architecture Reading |  | L-4.0 | 5 | 34659.6 | 173298 | PP(1.2) Surcharge
0
Labor Cost Subtotal | [8 empty] | 1191728.5957
Discount Amount | [8 empty] | 59586.4298 | 5% discount (previously agreed upon for OOO reasons) | Reason for discount
Expenses |  | Travel/reporting/meeting expenses
Total (VAT excluded) | [8 empty] | 1132142.1659
What to expect |  | 1) This quotation is for this case only and is valid for 30 days from the date of quotation.
見積書
Seoul, Gangseo-gu, Magokjungang8-ro 71 CEO : Hyun Shin Kyun
This quotation is for reference only
Formulas and values can be freely modified.
※ Please attach the actual quotation submitted by each customer when requesting CPapproval.
(LG Chem, Energy Solution IT Investment Plan)
Note on L20: 시장단가, P.P단가 등은 직접입력하세요.

## (3) MM-based quotation
* Please fill out only the area. (Please use only the areas that should be carried out under the M/M contract (PI/consulting, facility provision/exam, infrastructure installation/exam, analysis/design or exam only, solution purchase/setup, roll-in/out, dispatch of manpower to customer companies, etc.).)
Job Description |  |  | Belong | Technical Competency | Compensation |  |  | Total Input Airlift(M/M) | Gun Master (1 thousand won) | Monthly Input Details(M/M) |  |  |  |  | Remarks
category | Classification of duties | Job Description and Role |  | level | PP Eligibility | Surcharge Rate | Unit |  |  | M1 (O) | M2 (O) | M3 (O) | …... | MO (O)
sum | [7 empty] | 21.5 | 492918.75 | 6 | 6.5 | 5.5 | 0 | 3.5
Facility OO Management | OO Setup | 5 AA facilities | LG CNS | L-3.0 | None of the above | 1 | 26164 | 4 | 104656 | 1 | 1 | 1 |  | 1
| OO Installation | 5 AA facilities | LG CNS | L-2.0 | Smart Factory | 1.05 | 21976.5 | 3.5 | 76917.75 | 1 | 1 | 1 |  | 0.5 | Smart Factory Business Surcharge Application
| OO Inspection | 5 AA facilities | LG CNS | L-3.0 | None of the above | 1 | 26164 | 2 | 52328 |  | 1 | 1
Roll-In | Applying Area O | Applies to 2 zones | Supplier | L-1.0 | None of the above | 1 | 16744 | 2.5 | 41860 | 1 | 1 | 0.5
[8 empty] | 2.5 | 0 | 1 | 1 | 0.5
PI/Consulting | Consulting |  | LG CNS | L-4.0 | Smart Factory | 1.05 | 32965.8 | 1 | 32965.8 | 1 |  |  |  |  | Smart Factory Business Surcharge Application
infrastructure | Infrastructure Installation |  | Supplier | L-3.0 | None of the above | 1 | 26164 | 1 | 26164 |  | 0.5 | 0.5
guitar | PerformanceExam | Dispatch of relevant experts | Supplier | L-3.0 | None of the above | 1 | 26164 | 1 | 26164 |  |  |  |  | 1 | Dispatch of relevant experts
administration | PM |  | LG CNS | L-4.0 | Smart Factory | 1.05 | 32965.8 | 4 | 131863.2 | 1 | 1 | 1 |  | 1 | Smart Factory Business Surcharge Application
※ If the input manpower is eligible for "Premium Pricing", please select whether or not you are eligible or not.

## Refer_Standard Effort
category | Uniform Standard Blank Check Table (MD)
| Development Type | Development Type | new | [5 empty] | change
| (Acronym) | (Full Name) | new | new | new | new | new | new | change | change | change | change | change | change
|  |  | C0 | C1 | C2 | C3 | C4 | C5 | C0 | C1 | C2 | C3 | C4 | C5
standard | WEB | Online_Web | 1.1 | 1.8 | 3.2 | 5 | 7.4 | 11.9 | 0.6 | 1 | 2.3 | 3.6 | 5.3 | 8.9
standard | CS | Online_C/S | 1.1 | 1.8 | 3.1 | 5 | 9.1 | 14.1 | 0.4 | 0.7 | 2 | 3.5 | 6 | 9.5
standard | BWC | Batch_Web/CS | 1.1 | 1.7 | 2.9 | 4.6 | 6.8 | 10.8 | 0.4 | 0.8 | 1.5 | 2.7 | 4.9 | 7.6
standard | BCV | Batch_Conversion | 1 | 1.8 | 2.8 | 7 | 12.6 | 19.6 | 0.4 | 0.5 | 1 | 2.7 | 4.9 | 7.6
standard | EMQ | EAI_MQ | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
standard | EWS | EAI_WebService | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
Pantos | EWI | EAI_Webmethod (Internal) | 1 | 1.5 | 2 | 2.5 | 7 | 10 | 0.5 | 0.75 | 1 | 1.5 | 5 | 7
Pantos | EWE | EAI_Webmethod (external) | 2 | 3 | 4 | 5 | 7 | 10 | 1 | 1.5 | 2 | 3 | 5 | 7
standard | DBO | DB_DBObject | 0.7 | 1.4 | 3.4 | 5.9 | 10.6 | 16.5 | 0.4 | 0.8 | 1.7 | 3.1 | 5.9 | 9
LGD | DTB | DB_Table | 0.7 | 0.9 | 1 | 1.1 | 1.4 | 1.5 | 0.7 | 0.9 | 1 | 1.1 | 1.4 | 1.5
standard | OCC | Oracle_Concurrent | 1 | 1.8 | 3.1 | 6.4 | 10.6 | 17 | 0.4 | 0.8 | 1.5 | 2.7 | 5.2 | 7.9
standard | OFO | Oracle_Form | 1.2 | 2.1 | 3.5 | 6.4 | 11.1 | 17.5 | 0.4 | 0.8 | 1.8 | 3.2 | 5.2 | 8.4
standard | OOA | Oracle_OAF | 1.2 | 2.1 | 3.5 | 6.4 | 11.1 | 17.5 | 0.4 | 0.8 | 1.8 | 3.2 | 5.2 | 8.4
standard | ORE | Oracle_ Report | 0.9 | 1.4 | 2.1 | 3.5 | 4.9 | 7.5 | 0.5 | 0.8 | 1.3 | 2 | 3.2 | 5.1
standard | OXM | Oracle_XML Publisher | 0.9 | 1.4 | 2.1 | 3.5 | 4.9 | 7.5 | 0.4 | 0.7 | 1.4 | 2.1 | 3.9 | 6
standard | ODQ | Oracle_Dynamic Query | 0.4 | 0.4 | 0.7 | 1.8 | 2.5 | 4.3 | 0.4 | 0.4 | 0.7 | 1.8 | 2.5 | 4.3
standard | OBP | Oracle_BPM | 0.9 | 1.6 | 2.9 | 5.3 | 8.1 | 13.4 | 0.5 | 0.8 | 1.4 | 2.7 | 4.1 | 6.8
standard | SON | SAP_Online | 1.5 | 2.5 | 5 | 7 | 12 | 19 | 0.9 | 1.5 | 3 | 5 | 7 | 11.8
standard | SWJ | SAP_Webdyn for JAVA | 0.9 | 1.5 | 2.6 | 4 | 5.9 | 9.4 | 0.5 | 0.9 | 1.9 | 2.8 | 4.3 | 7
standard | SRE | SAP_ Report | 0.8 | 1.5 | 3 | 6 | 9 | 15 | 0.6 | 1 | 2 | 3 | 6 | 9
standard | SBA | SAP_Batch | 0.6 | 1 | 2 | 3 | 4 | 6.4 | 0.4 | 0.6 | 1.2 | 1.8 | 2.5 | 4.1
standard | SEN | SAP_Enhancement | 0.6 | 1 | 2 | 3 | 5 | 8 | 0.4 | 0.5 | 1 | 2 | 3 | 5
standard | SIF | SAP_I/F | 0.5 | 1 | 3 | 5 | 8 | 13 | 0.4 | 0.5 | 1.5 | 3 | 5 | 8
standard | SEI | SAP_EAI_I/F | 0.6 | 1.9 | 4.4 | 6.3 | 10 | 16.3 | 0.5 | 1.3 | 2.5 | 3.8 | 6.3 | 10
standard | SBR | SAP_BW_Report | - | 1 | 2 | 2.5 | 3.5 | 4.5 | - | 0.5 | 1.2 | 1.6 | 2.1 | 2.6
standard | SBM | SAP_BW_I/F | - | 1.8 | 3 | 4.2 | 6 | 7.8 | - | 1.5 | 2 | 2.5 | 3.6 | 4.7
standard | SBI | SAP_BW_Cube Modeling | - | 2.5 | 4.1 | 5.9 | 8.9 | 12 | - | 1.6 | 2.5 | 3.6 | 5.4 | 7.2
standard | DEAR | DW_Arcplan | 1.4 | 2.1 | 4.9 | 7 | 8.4 | 13.9 | 0.5 | 0.8 | 1.8 | 3.2 | 4.2 | 7.4
standard | DEBO | DW_BO Report | 0.4 | 0.4 | 0.7 | 1.8 | 2.5 | 4.3 | 0.2 | 0.2 | 0.4 | 0.7 | 1.1 | 1.8
standard | DEES | DW_Essbase | 1.4 | 2.1 | 4.9 | 7 | 8.4 | 13.9 | 0.5 | 0.8 | 1.8 | 3.2 | 4.2 | 7.4
standard | DEMR | DW_MSTR Report | 0.4 | 0.4 | 0.7 | 1.8 | 2.5 | 4.3 | 0.2 | 0.2 | 0.4 | 0.7 | 1.1 | 1.8
standard | DEMM | DW_MSTR Meta | 1.1 | 1.8 | 2.5 | 4.6 | 7.7 | 12.3 | 0.4 | 0.7 | 1.1 | 2.1 | 3.5 | 5.6
standard | DEBR | DW_BI Report | 0.4 | 0.4 | 0.7 | 1.8 | 2.5 | 4.3 | 0.2 | 0.2 | 0.4 | 0.7 | 1.1 | 1.8
standard | DEBM | DW_BI Meta | 1.1 | 1.8 | 2.5 | 4.6 | 7.7 | 12.3 | 0.4 | 0.7 | 1.1 | 2.1 | 3.5 | 5.6
standard | DE Collection | DW_Ingestion ETL | 0.6 | 1.1 | 2.8 | 4.9 | 7.4 | 12.3 | 0.4 | 0.7 | 1.4 | 2.5 | 3.5 | 6
standard | DE Integration | DW_Consolidated Summary ETL | 1.1 | 1.8 | 3.2 | 5.6 | 8.4 | 14 | 0.4 | 0.7 | 1.4 | 2.7 | 4.2 | 6.9
standard | DE uni | DW_ Universe | 1.1 | 1.8 | 2.5 | 4.6 | 7.7 | 12.3 | 0.4 | 0.7 | 1.1 | 2.1 | 3.5 | 5.6
standard | RPA | RPA | 0.9 | 1.6 | 2.6 | 4.5 | 7.7 | 13 | 0.6 | 1.1 | 1.9 | 3.2 | 5.4 | 9.1
standard | MH | Mobile_WEB_FrontEnd | 1 | 2 | 4 | 6 | 10 | 15 | 0.5 | 1 | 2 | 4 | 8 | 12
standard | MA | Mobile_Android | 2 | 4 | 6 | 10 | 15 | 20 | 1 | 2 | 3 | 5 | 8 | 12
standard | MI | Mobile_iOS | 2 | 4 | 6 | 10 | 15 | 20 | 1 | 2 | 3 | 5 | 8 | 12
standard | EIOP | EDP_Ingestion_On-Premise | 0.5 | 0.52 | 0.54 | 0.56 | 0.59 | - | 0.3 | 0.31 | 0.32 | 0.34 | 0.35 | -
standard | EEOP | EDP_Enrich_On-Premise | 3.16 | 4.82 | 6.21 | 8.13 | - | - | 1.45 | 2.6 | 3.44 | 3.96 | - | -
standard | EIAG | EDP_Ingestion_AWS_GCP | 0.6 | 1.1 | 2.8 | 4.9 | 7.4 | - | 0.4 | 0.7 | 1.4 | 2.5 | 3.5 | -
standard | EEAG | EDP_Enrich_AWS_GCP | 1.1 | 1.8 | 3.2 | 5.6 | 8.4 | - | 0.4 | 0.7 | 1.4 | 2.7 | 4.2 | -
standard | EIL0 | EDP_Ingestion_L0 Datasets | C0: 2.2; C1: 2.7; C2: 3.6; C3: 4.4; C4: 6.5; C5: -; C5: -
standard | EEL1 | EDP_Enrich_L1 Datasets | C0: 2.2; C1: 3; C2: 4.5; C3: 6.6; C4: 10.2; C5: -; C5: -
standard | Other | Other | bar: C0 to C5

## Details Effort
Development Type | Development Type | New/CHA | Difficulty | Standard Development Man-Hours (VNB) | Standard Development Man-Hours (KR) | 1.7
WEB | Online_Web | New | C0 | 1.87 | 1.1 | FE | CHA: Change
WEB | Online_Web | New | C1 | 3.06 | 1.8
WEB | Online_Web | New | C2 | 5.44 | 3.2 |  | 6
WEB | Online_Web | New | C3 | 8.5 | 5
WEB | Online_Web | New | C4 | 12.58 | 7.4
WEB | Online_Web | New | C5 | 20.23 | 11.9
WEB | Online_Web | CHA | C0 | 1.02 | 0.6
WEB | Online_Web | CHA | C1 | 1.7 | 1
WEB | Online_Web | CHA | C2 | 3.91 | 2.3
WEB | Online_Web | CHA | C3 | 6.12 | 3.6
WEB | Online_Web | CHA | C4 | 9.01 | 5.3
WEB | Online_Web | CHA | C5 | 15.13 | 8.9
CS | Online_C/S | New | C0 | 1.87 | 1.1 | BE
CS | Online_C/S | New | C1 | 3.06 | 1.8
CS | Online_C/S | New | C2 | 5.27 | 3.1
CS | Online_C/S | New | C3 | 8.5 | 5
CS | Online_C/S | New | C4 | 15.47 | 9.1
CS | Online_C/S | New | C5 | 23.97 | 14.1
CS | Online_C/S | CHA | C0 | 0.68 | 0.4
CS | Online_C/S | CHA | C1 | 1.19 | 0.7
CS | Online_C/S | CHA | C2 | 3.4 | 2
CS | Online_C/S | CHA | C3 | 5.95 | 3.5
CS | Online_C/S | CHA | C4 | 10.2 | 6
CS | Online_C/S | CHA | C5 | 16.15 | 9.5
BWC | Batch_Web/CS | New | C0 | 1.87 | 1.1
BWC | Batch_Web/CS | New | C1 | 2.89 | 1.7
BWC | Batch_Web/CS | New | C2 | 4.93 | 2.9
BWC | Batch_Web/CS | New | C3 | 7.82 | 4.6
BWC | Batch_Web/CS | New | C4 | 11.56 | 6.8
BWC | Batch_Web/CS | New | C5 | 18.36 | 10.8
BWC | Batch_Web/CS | CHA | C0 | 0.68 | 0.4
BWC | Batch_Web/CS | CHA | C1 | 1.36 | 0.8
BWC | Batch_Web/CS | CHA | C2 | 2.55 | 1.5
BWC | Batch_Web/CS | CHA | C3 | 4.59 | 2.7
BWC | Batch_Web/CS | CHA | C4 | 8.33 | 4.9
BWC | Batch_Web/CS | CHA | C5 | 12.92 | 7.6
BIF | Batch_I/F | New | C0 | 1.02 | 0.6
BIF | Batch_I/F | New | C1 | 1.87 | 1.1
BIF | Batch_I/F | New | C2 | 3.57 | 2.1
BIF | Batch_I/F | New | C3 | 6.63 | 3.9
BIF | Batch_I/F | New | C4 | 12.58 | 7.4
BIF | Batch_I/F | New | C5 | 19.21 | 11.3
BIF | Batch_I/F | CHA | C0 | 0.68 | 0.4
BIF | Batch_I/F | CHA | C1 | 1.36 | 0.8
BIF | Batch_I/F | CHA | C2 | 2.55 | 1.5
BIF | Batch_I/F | CHA | C3 | 4.59 | 2.7
BIF | Batch_I/F | CHA | C4 | 8.84 | 5.2
BIF | Batch_I/F | CHA | C5 | 13.43 | 7.9
BCV | Batch_Conversion | New | C0 | 1.7 | 1
BCV | Batch_Conversion | New | C1 | 3.06 | 1.8
BCV | Batch_Conversion | New | C2 | 4.76 | 2.8
BCV | Batch_Conversion | New | C3 | 11.9 | 7
BCV | Batch_Conversion | New | C4 | 21.42 | 12.6
BCV | Batch_Conversion | New | C5 | 33.32 | 19.6
BCV | Batch_Conversion | CHA | C0 | 0.68 | 0.4
BCV | Batch_Conversion | CHA | C1 | 0.85 | 0.5
BCV | Batch_Conversion | CHA | C2 | 1.7 | 1
BCV | Batch_Conversion | CHA | C3 | 4.59 | 2.7
BCV | Batch_Conversion | CHA | C4 | 8.33 | 4.9
BCV | Batch_Conversion | CHA | C5 | 12.92 | 7.6
EMQ | EAI_MQ | New | C0 | 1.87 | 1.1
EMQ | EAI_MQ | New | C1 | 1.87 | 1.1
EMQ | EAI_MQ | New | C2 | 1.87 | 1.1
EMQ | EAI_MQ | New | C3 | 1.87 | 1.1
EMQ | EAI_MQ | New | C4 | 1.87 | 1.1
EMQ | EAI_MQ | New | C5 | 1.87 | 1.1
EMQ | EAI_MQ | CHA | C0 | 1.36 | 0.8
EMQ | EAI_MQ | CHA | C1 | 1.36 | 0.8
EMQ | EAI_MQ | CHA | C2 | 1.36 | 0.8
EMQ | EAI_MQ | CHA | C3 | 1.36 | 0.8
EMQ | EAI_MQ | CHA | C4 | 1.36 | 0.8
EMQ | EAI_MQ | CHA | C5 | 1.36 | 0.8
EWS | EAI_WebService | New | C0 | 3.06 | 1.8
EWS | EAI_WebService | New | C1 | 3.06 | 1.8
EWS | EAI_WebService | New | C2 | 3.06 | 1.8
EWS | EAI_WebService | New | C3 | 3.06 | 1.8
EWS | EAI_WebService | New | C4 | 3.06 | 1.8
EWS | EAI_WebService | New | C5 | 3.06 | 1.8
EWS | EAI_WebService | CHA | C0 | 2.21 | 1.3
EWS | EAI_WebService | CHA | C1 | 2.21 | 1.3
EWS | EAI_WebService | CHA | C2 | 2.21 | 1.3
EWS | EAI_WebService | CHA | C3 | 2.21 | 1.3
EWS | EAI_WebService | CHA | C4 | 2.21 | 1.3
EWS | EAI_WebService | CHA | C5 | 2.21 | 1.3
DBO | DB_DBObject | New | C0 | 1.19 | 0.7
DBO | DB_DBObject | New | C1 | 2.38 | 1.4
DBO | DB_DBObject | New | C2 | 5.78 | 3.4
DBO | DB_DBObject | New | C3 | 10.03 | 5.9
DBO | DB_DBObject | New | C4 | 18.02 | 10.6
DBO | DB_DBObject | New | C5 | 28.05 | 16.5
DBO | DB_DBObject | CHA | C0 | 0.68 | 0.4
DBO | DB_DBObject | CHA | C1 | 1.36 | 0.8
DBO | DB_DBObject | CHA | C2 | 2.89 | 1.7
DBO | DB_DBObject | CHA | C3 | 5.27 | 3.1
DBO | DB_DBObject | CHA | C4 | 10.03 | 5.9
DBO | DB_DBObject | CHA | C5 | 15.3 | 9
OCC | Oracle_Concurrent | New | C0 | 1.7 | 1
OCC | Oracle_Concurrent | New | C1 | 3.06 | 1.8
OCC | Oracle_Concurrent | New | C2 | 5.27 | 3.1
OCC | Oracle_Concurrent | New | C3 | 10.88 | 6.4
OCC | Oracle_Concurrent | New | C4 | 18.02 | 10.6
OCC | Oracle_Concurrent | New | C5 | 28.9 | 17
OCC | Oracle_Concurrent | CHA | C0 | 0.68 | 0.4
OCC | Oracle_Concurrent | CHA | C1 | 1.36 | 0.8
OCC | Oracle_Concurrent | CHA | C2 | 2.55 | 1.5
OCC | Oracle_Concurrent | CHA | C3 | 4.59 | 2.7
OCC | Oracle_Concurrent | CHA | C4 | 8.84 | 5.2
OCC | Oracle_Concurrent | CHA | C5 | 13.43 | 7.9
OFO | Oracle_Form | New | C0 | 2.04 | 1.2
OFO | Oracle_Form | New | C1 | 3.57 | 2.1
OFO | Oracle_Form | New | C2 | 5.95 | 3.5
OFO | Oracle_Form | New | C3 | 10.88 | 6.4
OFO | Oracle_Form | New | C4 | 18.87 | 11.1
OFO | Oracle_Form | New | C5 | 29.75 | 17.5
OFO | Oracle_Form | CHA | C0 | 0.68 | 0.4
OFO | Oracle_Form | CHA | C1 | 1.36 | 0.8
OFO | Oracle_Form | CHA | C2 | 3.06 | 1.8
OFO | Oracle_Form | CHA | C3 | 5.44 | 3.2
OFO | Oracle_Form | CHA | C4 | 8.84 | 5.2
OFO | Oracle_Form | CHA | C5 | 14.28 | 8.4
OOA | Oracle_OAF | New | C0 | 2.04 | 1.2
OOA | Oracle_OAF | New | C1 | 3.57 | 2.1
OOA | Oracle_OAF | New | C2 | 5.95 | 3.5
OOA | Oracle_OAF | New | C3 | 10.88 | 6.4
OOA | Oracle_OAF | New | C4 | 18.87 | 11.1
OOA | Oracle_OAF | New | C5 | 29.75 | 17.5
OOA | Oracle_OAF | CHA | C0 | 0.68 | 0.4
OOA | Oracle_OAF | CHA | C1 | 1.36 | 0.8
OOA | Oracle_OAF | CHA | C2 | 3.06 | 1.8
OOA | Oracle_OAF | CHA | C3 | 5.44 | 3.2
OOA | Oracle_OAF | CHA | C4 | 8.84 | 5.2
OOA | Oracle_OAF | CHA | C5 | 14.28 | 8.4
ORE | Oracle_ Report | New | C0 | 1.53 | 0.9
ORE | Oracle_ Report | New | C1 | 2.38 | 1.4
ORE | Oracle_ Report | New | C2 | 3.57 | 2.1
ORE | Oracle_ Report | New | C3 | 5.95 | 3.5
ORE | Oracle_ Report | New | C4 | 8.33 | 4.9
ORE | Oracle_ Report | New | C5 | 12.75 | 7.5
ORE | Oracle_ Report | CHA | C0 | 0.85 | 0.5
ORE | Oracle_ Report | CHA | C1 | 1.36 | 0.8
ORE | Oracle_ Report | CHA | C2 | 2.21 | 1.3
ORE | Oracle_ Report | CHA | C3 | 3.4 | 2
ORE | Oracle_ Report | CHA | C4 | 5.44 | 3.2
ORE | Oracle_ Report | CHA | C5 | 8.67 | 5.1
OXM | Oracle_XML Publisher | New | C0 | 1.53 | 0.9
OXM | Oracle_XML Publisher | New | C1 | 2.38 | 1.4
OXM | Oracle_XML Publisher | New | C2 | 3.57 | 2.1
OXM | Oracle_XML Publisher | New | C3 | 5.95 | 3.5
OXM | Oracle_XML Publisher | New | C4 | 8.33 | 4.9
OXM | Oracle_XML Publisher | New | C5 | 12.75 | 7.5
OXM | Oracle_XML Publisher | CHA | C0 | 0.68 | 0.4
OXM | Oracle_XML Publisher | CHA | C1 | 1.19 | 0.7
OXM | Oracle_XML Publisher | CHA | C2 | 2.38 | 1.4
OXM | Oracle_XML Publisher | CHA | C3 | 3.57 | 2.1
OXM | Oracle_XML Publisher | CHA | C4 | 6.63 | 3.9
OXM | Oracle_XML Publisher | CHA | C5 | 10.2 | 6
ODQ | Oracle_Dynamic Query | New | C0 | 0.68 | 0.4
ODQ | Oracle_Dynamic Query | New | C1 | 0.68 | 0.4
ODQ | Oracle_Dynamic Query | New | C2 | 1.19 | 0.7
ODQ | Oracle_Dynamic Query | New | C3 | 3.06 | 1.8
ODQ | Oracle_Dynamic Query | New | C4 | 4.25 | 2.5
ODQ | Oracle_Dynamic Query | New | C5 | 7.31 | 4.3
ODQ | Oracle_Dynamic Query | CHA | C0 | 0.68 | 0.4
ODQ | Oracle_Dynamic Query | CHA | C1 | 0.68 | 0.4
ODQ | Oracle_Dynamic Query | CHA | C2 | 1.19 | 0.7
ODQ | Oracle_Dynamic Query | CHA | C3 | 3.06 | 1.8
ODQ | Oracle_Dynamic Query | CHA | C4 | 4.25 | 2.5
ODQ | Oracle_Dynamic Query | CHA | C5 | 7.31 | 4.3
OBP | Oracle_BPM | New | C0 | 1.53 | 0.9
OBP | Oracle_BPM | New | C1 | 2.72 | 1.6
OBP | Oracle_BPM | New | C2 | 4.93 | 2.9
OBP | Oracle_BPM | New | C3 | 9.01 | 5.3
OBP | Oracle_BPM | New | C4 | 13.77 | 8.1
OBP | Oracle_BPM | New | C5 | 22.78 | 13.4
OBP | Oracle_BPM | CHA | C0 | 0.85 | 0.5
OBP | Oracle_BPM | CHA | C1 | 1.36 | 0.8
OBP | Oracle_BPM | CHA | C2 | 2.38 | 1.4
OBP | Oracle_BPM | CHA | C3 | 4.59 | 2.7
OBP | Oracle_BPM | CHA | C4 | 6.97 | 4.1
OBP | Oracle_BPM | CHA | C5 | 11.56 | 6.8
SON | SAP_Online | New | C0 | 2.55 | 1.5
SON | SAP_Online | New | C1 | 4.25 | 2.5
SON | SAP_Online | New | C2 | 8.5 | 5
SON | SAP_Online | New | C3 | 11.9 | 7
SON | SAP_Online | New | C4 | 20.4 | 12
SON | SAP_Online | New | C5 | 32.3 | 19
SON | SAP_Online | CHA | C0 | 1.53 | 0.9
SON | SAP_Online | CHA | C1 | 2.55 | 1.5
SON | SAP_Online | CHA | C2 | 5.1 | 3
SON | SAP_Online | CHA | C3 | 8.5 | 5
SON | SAP_Online | CHA | C4 | 11.9 | 7
SON | SAP_Online | CHA | C5 | 20.06 | 11.8
SRE | SAP_ Report | New | C0 | 1.36 | 0.8
SRE | SAP_ Report | New | C1 | 2.55 | 1.5
SRE | SAP_ Report | New | C2 | 5.1 | 3
SRE | SAP_ Report | New | C3 | 10.2 | 6
SRE | SAP_ Report | New | C4 | 15.3 | 9
SRE | SAP_ Report | New | C5 | 25.5 | 15
SRE | SAP_ Report | CHA | C0 | 1.02 | 0.6
SRE | SAP_ Report | CHA | C1 | 1.7 | 1
SRE | SAP_ Report | CHA | C2 | 3.4 | 2
SRE | SAP_ Report | CHA | C3 | 5.1 | 3
SRE | SAP_ Report | CHA | C4 | 10.2 | 6
SRE | SAP_ Report | CHA | C5 | 15.3 | 9
SBA | SAP_Batch | New | C0 | 1.02 | 0.6
SBA | SAP_Batch | New | C1 | 1.7 | 1
SBA | SAP_Batch | New | C2 | 3.4 | 2
SBA | SAP_Batch | New | C3 | 5.1 | 3
SBA | SAP_Batch | New | C4 | 6.8 | 4
SBA | SAP_Batch | New | C5 | 10.88 | 6.4
SBA | SAP_Batch | CHA | C0 | 0.68 | 0.4
SBA | SAP_Batch | CHA | C1 | 1.02 | 0.6
SBA | SAP_Batch | CHA | C2 | 2.04 | 1.2
SBA | SAP_Batch | CHA | C3 | 3.06 | 1.8
SBA | SAP_Batch | CHA | C4 | 4.25 | 2.5
SBA | SAP_Batch | CHA | C5 | 6.97 | 4.1
SEN | SAP_Enhancement | New | C0 | 1.02 | 0.6
SEN | SAP_Enhancement | New | C1 | 1.7 | 1
SEN | SAP_Enhancement | New | C2 | 3.4 | 2
SEN | SAP_Enhancement | New | C3 | 5.1 | 3
SEN | SAP_Enhancement | New | C4 | 8.5 | 5
SEN | SAP_Enhancement | New | C5 | 13.6 | 8
SEN | SAP_Enhancement | CHA | C0 | 0.68 | 0.4
SEN | SAP_Enhancement | CHA | C1 | 0.85 | 0.5
SEN | SAP_Enhancement | CHA | C2 | 1.7 | 1
SEN | SAP_Enhancement | CHA | C3 | 3.4 | 2
SEN | SAP_Enhancement | CHA | C4 | 5.1 | 3
SEN | SAP_Enhancement | CHA | C5 | 8.5 | 5
SIF | SAP_I/F | New | C0 | 0.85 | 0.5
SIF | SAP_I/F | New | C1 | 1.7 | 1
SIF | SAP_I/F | New | C2 | 5.1 | 3
SIF | SAP_I/F | New | C3 | 8.5 | 5
SIF | SAP_I/F | New | C4 | 13.6 | 8
SIF | SAP_I/F | New | C5 | 22.1 | 13
SIF | SAP_I/F | CHA | C0 | 0.68 | 0.4
SIF | SAP_I/F | CHA | C1 | 0.85 | 0.5
SIF | SAP_I/F | CHA | C2 | 2.55 | 1.5
SIF | SAP_I/F | CHA | C3 | 5.1 | 3
SIF | SAP_I/F | CHA | C4 | 8.5 | 5
SIF | SAP_I/F | CHA | C5 | 13.6 | 8
DEAR | DW_Arcplan | New | C0 | 2.38 | 1.4
DEAR | DW_Arcplan | New | C1 | 3.57 | 2.1
DEAR | DW_Arcplan | New | C2 | 8.33 | 4.9
DEAR | DW_Arcplan | New | C3 | 11.9 | 7
DEAR | DW_Arcplan | New | C4 | 14.28 | 8.4
DEAR | DW_Arcplan | New | C5 | 23.63 | 13.9
DEAR | DW_Arcplan | CHA | C0 | 0.85 | 0.5
DEAR | DW_Arcplan | CHA | C1 | 1.36 | 0.8
DEAR | DW_Arcplan | CHA | C2 | 3.06 | 1.8
DEAR | DW_Arcplan | CHA | C3 | 5.44 | 3.2
DEAR | DW_Arcplan | CHA | C4 | 7.14 | 4.2
DEAR | DW_Arcplan | CHA | C5 | 12.58 | 7.4
DEBO | DW_BO Report | New | C0 | 0.68 | 0.4
DEBO | DW_BO Report | New | C1 | 0.68 | 0.4
DEBO | DW_BO Report | New | C2 | 1.19 | 0.7
DEBO | DW_BO Report | New | C3 | 3.06 | 1.8
DEBO | DW_BO Report | New | C4 | 4.25 | 2.5
DEBO | DW_BO Report | New | C5 | 7.31 | 4.3
DEBO | DW_BO Report | CHA | C0 | 0.34 | 0.2
DEBO | DW_BO Report | CHA | C1 | 0.34 | 0.2
DEBO | DW_BO Report | CHA | C2 | 0.68 | 0.4
DEBO | DW_BO Report | CHA | C3 | 1.19 | 0.7
DEBO | DW_BO Report | CHA | C4 | 1.87 | 1.1
DEBO | DW_BO Report | CHA | C5 | 3.06 | 1.8
DEES | DW_Essbase | New | C0 | 2.38 | 1.4
DEES | DW_Essbase | New | C1 | 3.57 | 2.1
DEES | DW_Essbase | New | C2 | 8.33 | 4.9
DEES | DW_Essbase | New | C3 | 11.9 | 7
DEES | DW_Essbase | New | C4 | 14.28 | 8.4
DEES | DW_Essbase | New | C5 | 23.63 | 13.9
DEES | DW_Essbase | CHA | C0 | 0.85 | 0.5
DEES | DW_Essbase | CHA | C1 | 1.36 | 0.8
DEES | DW_Essbase | CHA | C2 | 3.06 | 1.8
DEES | DW_Essbase | CHA | C3 | 5.44 | 3.2
DEES | DW_Essbase | CHA | C4 | 7.14 | 4.2
DEES | DW_Essbase | CHA | C5 | 12.58 | 7.4
DEMR | DW_MSTR Report | New | C0 | 0.68 | 0.4
DEMR | DW_MSTR Report | New | C1 | 0.68 | 0.4
DEMR | DW_MSTR Report | New | C2 | 1.19 | 0.7
DEMR | DW_MSTR Report | New | C3 | 3.06 | 1.8
DEMR | DW_MSTR Report | New | C4 | 4.25 | 2.5
DEMR | DW_MSTR Report | New | C5 | 7.31 | 4.3
DEMR | DW_MSTR Report | CHA | C0 | 0.34 | 0.2
DEMR | DW_MSTR Report | CHA | C1 | 0.34 | 0.2
DEMR | DW_MSTR Report | CHA | C2 | 0.68 | 0.4
DEMR | DW_MSTR Report | CHA | C3 | 1.19 | 0.7
DEMR | DW_MSTR Report | CHA | C4 | 1.87 | 1.1
DEMR | DW_MSTR Report | CHA | C5 | 3.06 | 1.8
DEMM | DW_MSTR Meta | New | C0 | 1.87 | 1.1
DEMM | DW_MSTR Meta | New | C1 | 3.06 | 1.8
DEMM | DW_MSTR Meta | New | C2 | 4.25 | 2.5
DEMM | DW_MSTR Meta | New | C3 | 7.82 | 4.6
DEMM | DW_MSTR Meta | New | C4 | 13.09 | 7.7
DEMM | DW_MSTR Meta | New | C5 | 20.91 | 12.3
DEMM | DW_MSTR Meta | CHA | C0 | 0.68 | 0.4
DEMM | DW_MSTR Meta | CHA | C1 | 1.19 | 0.7
DEMM | DW_MSTR Meta | CHA | C2 | 1.87 | 1.1
DEMM | DW_MSTR Meta | CHA | C3 | 3.57 | 2.1
DEMM | DW_MSTR Meta | CHA | C4 | 5.95 | 3.5
DEMM | DW_MSTR Meta | CHA | C5 | 9.52 | 5.6
DEBR | DW_BI Report | New | C0 | 0.68 | 0.4
DEBR | DW_BI Report | New | C1 | 0.68 | 0.4
DEBR | DW_BI Report | New | C2 | 1.19 | 0.7
DEBR | DW_BI Report | New | C3 | 3.06 | 1.8
DEBR | DW_BI Report | New | C4 | 4.25 | 2.5
DEBR | DW_BI Report | New | C5 | 7.31 | 4.3
DEBR | DW_BI Report | CHA | C0 | 0.34 | 0.2
DEBR | DW_BI Report | CHA | C1 | 0.34 | 0.2
DEBR | DW_BI Report | CHA | C2 | 0.68 | 0.4
DEBR | DW_BI Report | CHA | C3 | 1.19 | 0.7
DEBR | DW_BI Report | CHA | C4 | 1.87 | 1.1
DEBR | DW_BI Report | CHA | C5 | 3.06 | 1.8
DEBM | DW_BI Meta | New | C0 | 1.87 | 1.1
DEBM | DW_BI Meta | New | C1 | 3.06 | 1.8
DEBM | DW_BI Meta | New | C2 | 4.25 | 2.5
DEBM | DW_BI Meta | New | C3 | 7.82 | 4.6
DEBM | DW_BI Meta | New | C4 | 13.09 | 7.7
DEBM | DW_BI Meta | New | C5 | 20.91 | 12.3
DEBM | DW_BI Meta | CHA | C0 | 0.68 | 0.4
DEBM | DW_BI Meta | CHA | C1 | 1.19 | 0.7
DEBM | DW_BI Meta | CHA | C2 | 1.87 | 1.1
DEBM | DW_BI Meta | CHA | C3 | 3.57 | 2.1
DEBM | DW_BI Meta | CHA | C4 | 5.95 | 3.5
DEBM | DW_BI Meta | CHA | C5 | 9.52 | 5.6
DE Collection | DW_Ingestion ETL | New | C0 | 1.02 | 0.6
DE Collection | DW_Ingestion ETL | New | C1 | 1.87 | 1.1
DE Collection | DW_Ingestion ETL | New | C2 | 4.76 | 2.8
DE Collection | DW_Ingestion ETL | New | C3 | 8.33 | 4.9
DE Collection | DW_Ingestion ETL | New | C4 | 12.58 | 7.4
DE Collection | DW_Ingestion ETL | New | C5 | 20.91 | 12.3
DE Collection | DW_Ingestion ETL | CHA | C0 | 0.68 | 0.4
DE Collection | DW_Ingestion ETL | CHA | C1 | 1.19 | 0.7
DE Collection | DW_Ingestion ETL | CHA | C2 | 2.38 | 1.4
DE Collection | DW_Ingestion ETL | CHA | C3 | 4.25 | 2.5
DE Collection | DW_Ingestion ETL | CHA | C4 | 5.95 | 3.5
DE Collection | DW_Ingestion ETL | CHA | C5 | 10.2 | 6
DE Integration | DW_Consolidated Summary ETL | New | C0 | 1.87 | 1.1
DE Integration | DW_Consolidated Summary ETL | New | C1 | 3.06 | 1.8
DE Integration | DW_Consolidated Summary ETL | New | C2 | 5.44 | 3.2
DE Integration | DW_Consolidated Summary ETL | New | C3 | 9.52 | 5.6
DE Integration | DW_Consolidated Summary ETL | New | C4 | 14.28 | 8.4
DE Integration | DW_Consolidated Summary ETL | New | C5 | 23.8 | 14
DE Integration | DW_Consolidated Summary ETL | CHA | C0 | 0.68 | 0.4
DE Integration | DW_Consolidated Summary ETL | CHA | C1 | 1.19 | 0.7
DE Integration | DW_Consolidated Summary ETL | CHA | C2 | 2.38 | 1.4
DE Integration | DW_Consolidated Summary ETL | CHA | C3 | 4.59 | 2.7
DE Integration | DW_Consolidated Summary ETL | CHA | C4 | 7.14 | 4.2
DE Integration | DW_Consolidated Summary ETL | CHA | C5 | 11.73 | 6.9
DE uni | DW_ Universe | New | C0 | 1.87 | 1.1
DE uni | DW_ Universe | New | C1 | 3.06 | 1.8
DE uni | DW_ Universe | New | C2 | 4.25 | 2.5
DE uni | DW_ Universe | New | C3 | 7.82 | 4.6
DE uni | DW_ Universe | New | C4 | 13.09 | 7.7
DE uni | DW_ Universe | New | C5 | 20.91 | 12.3
DE uni | DW_ Universe | CHA | C0 | 0.68 | 0.4
DE uni | DW_ Universe | CHA | C1 | 1.19 | 0.7
DE uni | DW_ Universe | CHA | C2 | 1.87 | 1.1
DE uni | DW_ Universe | CHA | C3 | 3.57 | 2.1
DE uni | DW_ Universe | CHA | C4 | 5.95 | 3.5
DE uni | DW_ Universe | CHA | C5 | 9.52 | 5.6
RPA | RPA | New | C0 | 1.53 | 0.9
RPA | RPA | New | C1 | 2.72 | 1.6
RPA | RPA | New | C2 | 4.42 | 2.6
RPA | RPA | New | C3 | 7.65 | 4.5
RPA | RPA | New | C4 | 13.09 | 7.7
RPA | RPA | New | C5 | 22.1 | 13
RPA | RPA | CHA | C0 | 1.02 | 0.6
RPA | RPA | CHA | C1 | 1.87 | 1.1
RPA | RPA | CHA | C2 | 3.23 | 1.9
RPA | RPA | CHA | C3 | 5.44 | 3.2
RPA | RPA | CHA | C4 | 9.18 | 5.4
RPA | RPA | CHA | C5 | 15.47 | 9.1
EWI | EAI_Webmethod (Internal) | New | C0 | 1.7 | 1
EWI | EAI_Webmethod (Internal) | New | C1 | 2.55 | 1.5
EWI | EAI_Webmethod (Internal) | New | C2 | 3.4 | 2
EWI | EAI_Webmethod (Internal) | New | C3 | 4.25 | 2.5
EWI | EAI_Webmethod (Internal) | New | C4 | 11.9 | 7
EWI | EAI_Webmethod (Internal) | New | C5 | 17 | 10
EWI | EAI_Webmethod (Internal) | CHA | C0 | 0.85 | 0.5
EWI | EAI_Webmethod (Internal) | CHA | C1 | 1.275 | 0.75
EWI | EAI_Webmethod (Internal) | CHA | C2 | 1.7 | 1
EWI | EAI_Webmethod (Internal) | CHA | C3 | 2.55 | 1.5
EWI | EAI_Webmethod (Internal) | CHA | C4 | 8.5 | 5
EWI | EAI_Webmethod (Internal) | CHA | C5 | 11.9 | 7
EWE | EAI_Webmethod (external) | New | C0 | 3.4 | 2
EWE | EAI_Webmethod (external) | New | C1 | 5.1 | 3
EWE | EAI_Webmethod (external) | New | C2 | 6.8 | 4
EWE | EAI_Webmethod (external) | New | C3 | 8.5 | 5
EWE | EAI_Webmethod (external) | New | C4 | 11.9 | 7
EWE | EAI_Webmethod (external) | New | C5 | 17 | 10
EWE | EAI_Webmethod (external) | CHA | C0 | 1.7 | 1
EWE | EAI_Webmethod (external) | CHA | C1 | 2.55 | 1.5
EWE | EAI_Webmethod (external) | CHA | C2 | 3.4 | 2
EWE | EAI_Webmethod (external) | CHA | C3 | 5.1 | 3
EWE | EAI_Webmethod (external) | CHA | C4 | 8.5 | 5
EWE | EAI_Webmethod (external) | CHA | C5 | 11.9 | 7
DTB | DB_Table | New | C0 | 1.19 | 0.7
DTB | DB_Table | New | C1 | 1.53 | 0.9
DTB | DB_Table | New | C2 | 1.7 | 1
DTB | DB_Table | New | C3 | 1.87 | 1.1
DTB | DB_Table | New | C4 | 2.38 | 1.4
DTB | DB_Table | New | C5 | 2.55 | 1.5
DTB | DB_Table | CHA | C0 | 1.19 | 0.7
DTB | DB_Table | CHA | C1 | 1.53 | 0.9
DTB | DB_Table | CHA | C2 | 1.7 | 1
DTB | DB_Table | CHA | C3 | 1.87 | 1.1
DTB | DB_Table | CHA | C4 | 2.38 | 1.4
DTB | DB_Table | CHA | C5 | 2.55 | 1.5
SBR | SAP_BW_Report | New | C0 |  | -
SBR | SAP_BW_Report | New | C1 | 1.7 | 1
SBR | SAP_BW_Report | New | C2 | 3.4 | 2
SBR | SAP_BW_Report | New | C3 | 4.25 | 2.5
SBR | SAP_BW_Report | New | C4 | 5.95 | 3.5
SBR | SAP_BW_Report | New | C5 | 7.65 | 4.5
SBR | SAP_BW_Report | CHA | C0 |  | -
SBR | SAP_BW_Report | CHA | C1 | 0.85 | 0.5
SBR | SAP_BW_Report | CHA | C2 | 2.04 | 1.2
SBR | SAP_BW_Report | CHA | C3 | 2.72 | 1.6
SBR | SAP_BW_Report | CHA | C4 | 3.57 | 2.1
SBR | SAP_BW_Report | CHA | C5 | 4.42 | 2.6
SBM | SAP_BW_I/F | New | C0 |  | -
SBM | SAP_BW_I/F | New | C1 | 3.06 | 1.8
SBM | SAP_BW_I/F | New | C2 | 5.1 | 3
SBM | SAP_BW_I/F | New | C3 | 7.14 | 4.2
SBM | SAP_BW_I/F | New | C4 | 10.2 | 6
SBM | SAP_BW_I/F | New | C5 | 13.26 | 7.8
SBM | SAP_BW_I/F | CHA | C0 |  | -
SBM | SAP_BW_I/F | CHA | C1 | 2.55 | 1.5
SBM | SAP_BW_I/F | CHA | C2 | 3.4 | 2
SBM | SAP_BW_I/F | CHA | C3 | 4.25 | 2.5
SBM | SAP_BW_I/F | CHA | C4 | 6.12 | 3.6
SBM | SAP_BW_I/F | CHA | C5 | 7.99 | 4.7
SBI | SAP_BW_Cube Modeling | New | C0 |  | -
SBI | SAP_BW_Cube Modeling | New | C1 | 4.25 | 2.5
SBI | SAP_BW_Cube Modeling | New | C2 | 6.97 | 4.1
SBI | SAP_BW_Cube Modeling | New | C3 | 10.03 | 5.9
SBI | SAP_BW_Cube Modeling | New | C4 | 15.13 | 8.9
SBI | SAP_BW_Cube Modeling | New | C5 | 20.4 | 12
SBI | SAP_BW_Cube Modeling | CHA | C0 |  | -
SBI | SAP_BW_Cube Modeling | CHA | C1 | 2.72 | 1.6
SBI | SAP_BW_Cube Modeling | CHA | C2 | 4.25 | 2.5
SBI | SAP_BW_Cube Modeling | CHA | C3 | 6.12 | 3.6
SBI | SAP_BW_Cube Modeling | CHA | C4 | 9.18 | 5.4
SBI | SAP_BW_Cube Modeling | CHA | C5 | 12.24 | 7.2
MA | Mobile_Android | New | C0 | 3.4 | 2
MA | Mobile_Android | New | C1 | 6.8 | 4
MA | Mobile_Android | New | C2 | 10.2 | 6
MA | Mobile_Android | New | C3 | 17 | 10
MA | Mobile_Android | New | C4 | 25.5 | 15
MA | Mobile_Android | New | C5 | 34 | 20
MA | Mobile_Android | CHA | C0 | 1.7 | 1
MA | Mobile_Android | CHA | C1 | 3.4 | 2
MA | Mobile_Android | CHA | C2 | 5.1 | 3
MA | Mobile_Android | CHA | C3 | 8.5 | 5
MA | Mobile_Android | CHA | C4 | 13.6 | 8
MA | Mobile_Android | CHA | C5 | 20.4 | 12
MI | Mobile_iOS | New | C0 | 3.4 | 2
MI | Mobile_iOS | New | C1 | 6.8 | 4
MI | Mobile_iOS | New | C2 | 10.2 | 6
MI | Mobile_iOS | New | C3 | 17 | 10
MI | Mobile_iOS | New | C4 | 25.5 | 15
MI | Mobile_iOS | New | C5 | 34 | 20
MI | Mobile_iOS | CHA | C0 | 1.7 | 1
MI | Mobile_iOS | CHA | C1 | 3.4 | 2
MI | Mobile_iOS | CHA | C2 | 5.1 | 3
MI | Mobile_iOS | CHA | C3 | 8.5 | 5
MI | Mobile_iOS | CHA | C4 | 13.6 | 8
MI | Mobile_iOS | CHA | C5 | 20.4 | 12
MH | Mobile_WEB_FrontEnd | New | C0 | 1.7 | 1
MH | Mobile_WEB_FrontEnd | New | C1 | 3.4 | 2
MH | Mobile_WEB_FrontEnd | New | C2 | 6.8 | 4
MH | Mobile_WEB_FrontEnd | New | C3 | 10.2 | 6
MH | Mobile_WEB_FrontEnd | New | C4 | 17 | 10
MH | Mobile_WEB_FrontEnd | New | C5 | 25.5 | 15
MH | Mobile_WEB_FrontEnd | CHA | C0 | 0.85 | 0.5
MH | Mobile_WEB_FrontEnd | CHA | C1 | 1.7 | 1
MH | Mobile_WEB_FrontEnd | CHA | C2 | 3.4 | 2
MH | Mobile_WEB_FrontEnd | CHA | C3 | 6.8 | 4
MH | Mobile_WEB_FrontEnd | CHA | C4 | 13.6 | 8
MH | Mobile_WEB_FrontEnd | CHA | C5 | 20.4 | 12
EIOP | EDP_Ingestion_On-Premise | New | C0 | 0.85 | 0.5
EIOP | EDP_Ingestion_On-Premise | New | C1 | 0.884 | 0.52
EIOP | EDP_Ingestion_On-Premise | New | C2 | 0.918 | 0.54
EIOP | EDP_Ingestion_On-Premise | New | C3 | 0.952 | 0.56
EIOP | EDP_Ingestion_On-Premise | New | C4 | 1.003 | 0.59
EIOP | EDP_Ingestion_On-Premise | New | C5 |  | -
EIOP | EDP_Ingestion_On-Premise | CHA | C0 | 0.51 | 0.3
EIOP | EDP_Ingestion_On-Premise | CHA | C1 | 0.527 | 0.31
EIOP | EDP_Ingestion_On-Premise | CHA | C2 | 0.544 | 0.32
EIOP | EDP_Ingestion_On-Premise | CHA | C3 | 0.578 | 0.34
EIOP | EDP_Ingestion_On-Premise | CHA | C4 | 0.595 | 0.35
EIOP | EDP_Ingestion_On-Premise | CHA | C5 |  | -
EEOP | EDP_Enrich_On-Premise | New | C0 | 5.372 | 3.16
EEOP | EDP_Enrich_On-Premise | New | C1 | 8.194 | 4.82
EEOP | EDP_Enrich_On-Premise | New | C2 | 10.557 | 6.21
EEOP | EDP_Enrich_On-Premise | New | C3 | 13.821 | 8.13
EEOP | EDP_Enrich_On-Premise | New | C4 |  | -
EEOP | EDP_Enrich_On-Premise | New | C5 |  | -
EEOP | EDP_Enrich_On-Premise | CHA | C0 | 2.465 | 1.45
EEOP | EDP_Enrich_On-Premise | CHA | C1 | 4.42 | 2.6
EEOP | EDP_Enrich_On-Premise | CHA | C2 | 5.848 | 3.44
EEOP | EDP_Enrich_On-Premise | CHA | C3 | 6.732 | 3.96
EEOP | EDP_Enrich_On-Premise | CHA | C4 |  | -
EEOP | EDP_Enrich_On-Premise | CHA | C5 |  | -
EIAG | EDP_Ingestion_AWS_GCP | New | C0 | 1.02 | 0.6
EIAG | EDP_Ingestion_AWS_GCP | New | C1 | 1.87 | 1.1
EIAG | EDP_Ingestion_AWS_GCP | New | C2 | 4.76 | 2.8
EIAG | EDP_Ingestion_AWS_GCP | New | C3 | 8.33 | 4.9
EIAG | EDP_Ingestion_AWS_GCP | New | C4 | 12.58 | 7.4
EIAG | EDP_Ingestion_AWS_GCP | New | C5 |  | -
EIAG | EDP_Ingestion_AWS_GCP | CHA | C0 | 0.68 | 0.4
EIAG | EDP_Ingestion_AWS_GCP | CHA | C1 | 1.19 | 0.7
EIAG | EDP_Ingestion_AWS_GCP | CHA | C2 | 2.38 | 1.4
EIAG | EDP_Ingestion_AWS_GCP | CHA | C3 | 4.25 | 2.5
EIAG | EDP_Ingestion_AWS_GCP | CHA | C4 | 5.95 | 3.5
EIAG | EDP_Ingestion_AWS_GCP | CHA | C5 |  | -
EEAG | EDP_Enrich_AWS_GCP | New | C0 | 1.87 | 1.1
EEAG | EDP_Enrich_AWS_GCP | New | C1 | 3.06 | 1.8
EEAG | EDP_Enrich_AWS_GCP | New | C2 | 5.44 | 3.2
EEAG | EDP_Enrich_AWS_GCP | New | C3 | 9.52 | 5.6
EEAG | EDP_Enrich_AWS_GCP | New | C4 | 14.28 | 8.4
EEAG | EDP_Enrich_AWS_GCP | New | C5 |  | -
EEAG | EDP_Enrich_AWS_GCP | CHA | C0 | 0.68 | 0.4
EEAG | EDP_Enrich_AWS_GCP | CHA | C1 | 1.19 | 0.7
EEAG | EDP_Enrich_AWS_GCP | CHA | C2 | 2.38 | 1.4
EEAG | EDP_Enrich_AWS_GCP | CHA | C3 | 4.59 | 2.7
EEAG | EDP_Enrich_AWS_GCP | CHA | C4 | 7.14 | 4.2
EEAG | EDP_Enrich_AWS_GCP | CHA | C5 |  | -
EIL0 | EDP_Ingestion_L0 Datasets | New | C0 | 3.74 | 2.2
EIL0 | EDP_Ingestion_L0 Datasets | New | C1 | 4.59 | 2.7
EIL0 | EDP_Ingestion_L0 Datasets | New | C2 | 6.12 | 3.6
EIL0 | EDP_Ingestion_L0 Datasets | New | C3 | 7.48 | 4.4
EIL0 | EDP_Ingestion_L0 Datasets | New | C4 | 11.05 | 6.5
EIL0 | EDP_Ingestion_L0 Datasets | New | C5 |  | -
EEL1 | EDP_Enrich_L1 Datasets | New | C0 | 3.74 | 2.2
EEL1 | EDP_Enrich_L1 Datasets | New | C1 | 5.1 | 3
EEL1 | EDP_Enrich_L1 Datasets | New | C2 | 7.65 | 4.5
EEL1 | EDP_Enrich_L1 Datasets | New | C3 | 11.22 | 6.6
EEL1 | EDP_Enrich_L1 Datasets | New | C4 | 17.34 | 10.2
EEL1 | EDP_Enrich_L1 Datasets | New | C5 |  | -
guitar | guitar | New | UD | UD | UD

## Difficulty (Complexity)
[Web] |  |  | 4mh
Processing Type | entry | C1 | C2 | C3 | C4 | C5
Online | Table (Except coded) | . No more than 2 | . No more than 3 | . 4 or less | . 5 or more | . Complexity4 or higher If there is a need for consultation
| Number of columns/items (Screen, Handing) | . No more than 10 | . 10~20 | . 15~25 | . 25 or more
| Processing complexity (Validation Note 1> | . No more than 5 | . 6 ~ 10 | . 11~15 | . More than 15
| Processing complexity 1) Number of work logic 2) 2) Calculation Note 3) 3) Screen Function Note 4) | . none | . 1~5 | . 6~10 | . Over 10
| UI elements (common) | . Design, alignment, etc.
| Others/Examples | . Common Excel Download features . Simple inquiry without calculation (e.g. number inquiry) | . Normal List lookup with calculations . Create a simple icon menu - if you only have an on-screen UI and an image . If you don't have a major logic in your business . Simple input, modification screen, simple join, and processing screen for query results | . Changing and Adding Table Columns . If there is an important logic of the work . When the complexity of the design requires a lot of manual assembly . If a specific function is required, such as sorting by column, a screen with a page function, etc. | . Data Upload Processing Screen (Upload Data Using Files) . When there is validation complexity according to the important logic of the business | . When it is necessary to link external devices, function modules provided by companies, open APIs, etc. . If there is a requirement that needs to be implemented by applying the device . If you have a configuration request for your own security and cryptographic modules . In the event of a special occurrence such as the introduction of a solution . Perform highly complex logic, control external hardware, and apply new technologies
Batch/ Conversion | Table | . No more than 2 | . 3 pcs | . 4 pcs | . 5 pcs | . 6 or more
| Processing complexity (Calculation & Check Process) | . No more than 2 times | . E3 | . E4 | . E5 | . More than 6 times
| Processing complexity (Transaction) | . none | . 1~2pcs | . 3~4pcs | . 5~6pcs | . 7 or more
| Other Considerations (Difficulty Increase) | . External Systems, External Links . vs. Capacity Data Processing (Performance, Validation, Exception Data) . Consider I/F method complexity (MQ, WebService, EAI, B2Bi)
Note 1) The number of alerts or JavaScript processed at the screen level (Check) |  |  | Note 3) Average, Sum, Deviation, etc.
Note 2) There is no special business logic such as branching or processing by type in Server Logic. |  |  | Note 4) Screen link, Reset, paging processing, file attachment, sorting function, mailing, etc.
[Oracle ERP]
Processing Type | entry | C1 | C2 | C3 | C4 | C5
Online | Number of Tables (Except coded) | No more than 1 | 2~3 or less | 4~5 or less | More than 5 | - Complexity4 or higher If there is a special matter and a consultation is required
| Validation(Logic) & Input Fields | No more than 10 | No more than 15 | No more than 20 | More than 20
| Form UI 1) | unity | 3 or less | 5 or less | Over 5
| Standard API | 0 | 1 | 2 | Over 2
| common | - UI elements: Design, Align, etc. - OAF construction reflects a 1 level increase compared to Form building difficulty (?)
| Others/Examples | - Pure BD/UT workload of about 1 day - No special logic required - Single SQL, Report that requires minimal format changes | - Pure BD/UT workload of about 2 days - When it is necessary to reflect logic such as implementing simple calculations or editing. - Data from 1~2 tables Selection Logic and some formatting is required | - Pure BD/UT about 3 days of workload - When you need to reflect the logic of performing various calculations, other screen calls, etc. - Report using form paper (fixed print type) - Report with a lot of data selection and formatting from several tables with master-detail structure | - Pure BD/UT about 5 days of workload - When you need to implement a variety of complex functions and call a separate program. - You need to implement functionality that is not standard in Oracle Forms. - Report using form paper (fixed print type) - Complex data processing logic and formatting are required, and many tables and hierarchies between them are complex, so mutual validation is required | - Complexity4 or higher If there is a special matter and a consultation is required - You need to implement functionality that is not provided by the standard. - When it is necessary to link external devices, function modules provided by companies, open APIs, etc. - When there is a requirement that needs to be implemented by applying the device - If there is a request to configure your own security and cryptographic modules - In case of special issues such as solution introduction - Perform highly complex logic, control external hardware, apply new technologies
Batch |  | - Pure BD/UT workload of about 1 day - If only a single table is possible. For example, a Database Trigger that adds a single row to another table. - Add/edit conditions and fields | - Pure BD/UT workload of about 2 days - When updating 2~3 tables by looping or simple conditions, - If there are less than 2 internal objects (Func, Proc) when configured as a package, - When mapping data dependent on a module and interfacing it | - Pure BD/UT about 3 days of workload - When looping, calculating, or updating more than 3 tables by condition - When configured as a package, if there are 3 ~ 5 internal objects (Func, Proc) - When considering and interfacing with business processes of more than 1,2 modules | - Pure BD/UT about 5 days of workload - When updating more than 5 tables with logic such as complex conditions - If there are more than 5 internal objects (Func, Proc) when configured as a package, | - Complexity4 or higher If there is a special matter and a consultation is required - When the Standard API call logic is applied.
common
| Other considerations (difficulty upgrades) | - External systems, external linkage - Handling large capacity data (performance, validation, exception data)
Conversion |  | - Pure BD/UT workload of about 1 day - Application of simple codes, such as standard codes | - Pure BD/UT workload of about 2 days - Apply 3~5 columns to 1 table - If conversion is required after mapping in the Extension Table. | - Pure BD/UT about 3 days of workload - Bulk registration of large capacity data - Apply Converstion to 2~3 tables - When two or more business processes are considered and conversion is required after mapping | - Pure BD/UT about 5 days of workload - When a data transformation operation is applied to two or more tables. - If there are 3~4 conversion linked tables - When it is necessary to convert after mapping in consideration of 3 or more business processes | - Complexity4 or higher If there is a special matter and a consultation is required - When applying History and Transaction data, data processing occurs and there are more than 5 linked tables.
Note 1) Form UI : Tab, Stacked, Dynamic View
[C/S]
Processing Type | entry | C1 | C2 | C3 | C4 | C5 | Class Description
Online |  | - If there is no major logic in the business - Simple inquiry within 2~3 tables, simple calculation - If there is no change in the DB Object. | - Processing of simple transactions in about 3 tables - If there are less than 5 validation checks according to the important logic of the business - Table column changes and additions occur - When CRUD functions are interrelated, Excel processing, etc. | - When 4 or fewer tables are linked and transaxtion occurs. - If there is an addition of special functions - If there are more than 5 validation checks according to the important logic of the work - Creating tables, changing columns, and adding - The correlation of CRUD functions is complex. | - When more than 5 tables are linked to create a complex transaxtion - If there is a special function or exception function added - If there are more than 5 validation checks according to the important logic of the work or if there are many branches of the work logic - Creating tables, changing columns, and adding - Implemented with technology that lacks experience and competence | - Complexity4 or higher If there is a special matter and a consultation is required When screen configuration (tap configuration, etc.) and logic processing are very complex and require long-term verification When there is a lot of linkage between other systems and it is complicated, communication with the outside world occurs Application of new technologies that have not been experienced, application of solutions, etc. | Program for User Interface for Client ▶ Development of process UI screen for MES ▶ Configure screen layout such as list inquiry and detailed inquiry Display item definition ▶ Invoke business logic or invoke the DB's Stored Procedure ▶ Organize your screen, including images ▶ Includes other types of I/F including PLC and signal processing items
Batch | Table | . No more than 2 | . 3 pcs | . 4 pcs | . 5 pcs | . 6 or more | Processing the work logic that the system triggrings Large-scale batch processing
| Processing complexity (Calculation & Check Process) | . No more than 2 times | . E3 | . E4 | . E5 | . More than 6 times
| Processing complexity (Transaction) | . none | . 1~2pcs | . 3~4pcs | . 5~6pcs | . 7 or more
| Other Considerations (Difficulty Increase) | . External Systems, External Links . vs. Capacity Data Processing (Performance, Validation, Exception Data) . Consider I/F method complexity (MQ, WebService, EAI, B2Bi)
[DW]
category | C1 | C2 | C3 | C4 | C5 | Describe the criteria (simple logic) | Describe criteria (complex logic)
Ingestion ETL | 1~2 tables, and if you handle simple logic | - Refer to 3~4 tables, and handle simple logic - Refer to 1~2 tables, and when processing complex logic | - Refer to 5~6 tables, and if you are dealing with simple logic - Refer to 3~4 tables, and handle complex logic | - Refer to more than 7 tables, and handle simple/complex logic - Refer to 5~6 tables, and handle complex logic | . Complexity4 or higher If there is a need for consultation | -If you are using Generated SQL -DB, if you are using the default function provided | -User Defined: If you're using SQL -If you have a parallel processing job (PX job)
Consolidated Summary ETL | 1~2 tables, and if you handle simple logic | - Refer to 3~4 tables, and handle simple logic - Refer to 1~2 tables, and when processing complex logic | - Refer to 5~6 tables, and if you are dealing with simple logic - Refer to 3~4 tables, and handle complex logic | - Refer to more than 7 tables, and handle simple/complex logic - Refer to 5~6 tables, and handle complex logic | . Complexity4 or higher If there is a need for consultation | - If you use source tables and columns without variations, or if you use simple mapping logic | -When using advanced ETL features such as hash functions -If you have a parallel processing job (PX job)
Universe | 1 table, and if you are dealing with simple logic, | - Refer to 2~3 tables, and if you are dealing with simple logic - Referring to 1 table, when dealing with complex logic | -Refer to 4~5 tables, and if you are dealing with simple logic -Refer to 2~3 tables, and if you are dealing with complex logic | - Refer to more than 6 tables, and handle simple/complex logic - Refer to 4~5 tables, and handle complex logic | . Complexity4 or higher If there is a need for consultation | - if you are referencing a physical table or View without any variations | -If you are referencing a derived table (a View formed by separate logic)
BO Report | If you refer to 1 universe and handle simple logic | - If you refer to 2 universes and handle simple logic - When referring to 1 universe and processing complex logic | - 3 universes, if you are dealing with simple logic - Refer to 2 universes, and if you are dealing with complex logic. | - When referring to more than 4 universes and dealing with simple/complex logic - When referring to 3 universes and dealing with complex logic | . Complexity4 or higher If there is a need for consultation | - If you are using a basic chart, do not use variables, or if the design application is simple | -Capacity when processing data -If you are using a customized chart, using a large number of variables, or applying a complex design
MSTR Meta | - Refer to 1~5 dimension tables, and handle simple logic | - Refer to 6~10 dimension tables, and handle simple logic - Refer to 1~5 dimension tables, and handle complex logic | - Refer to 11~15 dimension tables, and handle simple logic - Refer to 6~10 dimension tables, and handle complex logic | - Referring to more than 16 dimension tables, and processing simple logic - Refer to 11~15 dimension tables, and handle complex logic | . Complexity4 or higher If there is a need for consultation | - When creating schema objects using source tables and columns without variations, or when using simple mapping logic when creating public objects. | -When creating a schema object, the source table and columns are formed with separate logic, or the number of metrics is more than 30.
MSTR Report | 1-10 MSTR objects, and if you are dealing with simple logic, | - 11~20 MSTR objects, and simple logic is processed - 1~10 MSTR objects, and when processing complex logic | - 21~30 MSTR objects, and simple logic is processed - 11~20 MSTR objects, and when processing complex logic | - Referencing more than 31 MSTR objects, and processing simple logic - Referencing 21~30 MSTR objects, and processing complex logic | . Complexity4 or higher If there is a need for consultation | - Use default Attributes, Metrics, or use no variables, or if the design application is simple. | -If the metric logic is complex, if you use complex (derived) Metrics, if you use a large number of variables, or if you apply a complex design.
BI Report | 1 table, no more than 5 columns | - No more than 2 tables, no more than 10 columns, and no more than 5 calculations and check processes | - No more than 3 tables, no more than 20 columns, and no more than 10 calculation and check processes | - No more than 4 tables, no more than 25 columns, and no more than 15 calculation and check processes. | . Complexity4 or higher If there is a need for consultation
BI Meta | 1 table, no more than 10 columns | - No more than 2 tables, no more than 15 columns, and no more than 5 calculations and check processes | - No more than 3 tables, no more than 20 columns, and no more than 10 calculation and check processes | - No more than 4 tables, no more than 25 columns, and no more than 15 calculation and check processes. | . Complexity4 or higher If there is a need for consultation
Essbase | 1~5 tables, and if you are dealing with simple logic | - Refer to 6~7 tables, and handle simple logic - Refer to 1~5 tables, and if you are dealing with complex logic | - Refer to 8~9 tables, and handle simple logic - Refer to 6~7 tables, and when dealing with complex logic | - Refer to more than 10 tables, and handle simple/complex logic - Refer to 8~9 tables, and if you are dealing with complex logic | . Complexity4 or higher If there is a need for consultation | -When using simple rollup functions such as SUM/AVG | -When using the Custom Calc function or implementing complex computational logic (daily calculation)
Arcplan | 1 table, and if you are dealing with simple logic, | - Referencing 2 tables, and processing simple logic - Referring to 1 table, when dealing with complex logic | -3 tables, if you are dealing with simple logic. - Refers to 2 tables, if you are dealing with complex logic. | - Refer to more than 4 tables, and handle simple/complex logic - 3 tables, when dealing with complex logic | . Complexity4 or higher If there is a need for consultation | - If the data processing is simple, or if you are using the Arcplan basic chart | - If you have complex data processing logic or use customized charts - If you use internal DB to match the screen format
* If more than 50% of the new program needs to be modified
* Tables include facts and dimensions
[SAP ERP]
Processing Type | C1 | C2 | C3 | C4 | C5 | Class Description
Online | A simple process with fewer than 3 main functions or - Simple Validation Check for less than 5 items - Simple calculation and check process of less than 3 times - Fewer than 4 key table-related processes Simple screen with fewer than 3 screens - Fewer than 10 columns - Table Control | Complex processes with fewer than 3 main functions or - Complex Validation Checks for fewer than 5 items - Complex calculation and check processes of less than 3 times - Fewer than 4 key table-related processes - Less than 4 simple screen BDC processes - Simple screen development (Call Transtion, Submit..) Fewer than 3 screens, including complex screens - More than 10 columns. - Complex lists (Table Control) - Subscreen (Tab Control) - Simple Form Report (Smart Form, SAP Script) | A simple process with three or more main functions or - Simple Validation Check for more than 5 items - More than 3 simple calculation and check processes - More than 4 key table-related processes - More than 4 complex screen BDC processes 3 or more screens, and 2 or fewer complex screens - Fewer than 10 columns. - Table Control - Simple Form Report (Smart Form, SAP Script) | Complex processes with three or more main functions or - Complex validation checks for more than 5 items - More than 3 complex calculation and check processes - More than 4 key table-related processes - BDC process that performs two or more transactions 3 or more screens, and 3 or more complex screens - More than 10 columns. - Complex lists (Table Control) - Tab Control - Complex form reports (Smart Form, SAP Script) | . Complexity4 or higher If there is a need for consultation | A program that is further developed to meet the needs of users and CUD is generated through user input ▶ Module Pool ▶ User input via ALV Control ▶ A program that performs CUD through the user's input data (column data) on the screen [Remarks] ▶ Functional Unit: Logic for development, such as calculation/check, SQL complexity, number of SQL executions, and number of cases. ▶ Screen unit: Displays the complexity of the design aspect rather than the implementation logic aspect, and considers Report/Print forms such as SmartForm and SAPScript as screens. ▶ Main function: Refers to the sub screen of the program or the main function of the program. ▶ Screen: 1 screen when running SAP Transtion, and one screen for Sub Tab when using TAB. The number of tables is not included on the screen
Report | A simple process with fewer than 3 main functions or - Simple calculation and check process of less than 3 times - Fewer than 4 key table-related processes Simple screen with fewer than 3 screens - Simple lists. | Complex processes with fewer than 3 main functions or - Complex calculation and check processes of less than 3 times - Fewer than 4 key table-related processes - Less than 4 simple screen BDC processes - Simple screen development (Call Transtion, Submit..) Fewer than 3 screens, including complex screens - Complex lists (trees) - Complex report forms - Simple Smart Form, SAP Script | A simple process with three or more main functions or - More than 3 simple calculation and check processes - More than 4 key table-related processes - More than 4 complex screen BDC processes 3 or more screens, and 2 or fewer complex screens - Simple lists. - Simple Smart Form, SAP Script | Complex processes with three or more main functions or - More than 3 complex calculation and check processes - More than 4 key table-related processes - BDC process that performs two or more transactions 3 or more screens, and 3 or more complex screens - Complex lists (trees) - Complex report forms - Complex Smart Forms, SAP Script | . Complexity4 or higher If there is a need for consultation | A program that inquires data that meets certain conditions according to the user's needs or executes the scheduling process ▶ Report / Statistical Inquiry Program ▶ After list inquiry, implement additional functions such as detailed inquiry, status change, approval, and release ▶ Implementation of additional functions through selection, checking, etc. without user input on the screen ▶ ABAP Query
Batch | Simple process - Process by simple inquiry or source file - Simple calculation and check process of less than 3 times - Fewer than 4 key table-related processes | A process with simple logic added - Complex calculation and check processes of less than 3 times - BDC using 1 simple transaction - Fewer than 4 major table-related processes | Processes with complex logic added - View more than 4 related table information for additional information after file upload - More than 4 simple calculation and check processes - BDCs that use less than 3 transactions and contain complex screens - More than 4 major table-related processes | Complex processes that perform multiple functions - BDCs that use 3 or more complex transactions - More than 4 complex calculation and check processes - Other complex processes.. | . Complexity4 or higher If there is a need for consultation | Programs developed further for the processing of large amounts of data using native programs in SAP R/3 or for the convenience of users. ▶ Multi-data control through file upload for reflection of basic data or master data ▶ Batch Program with Schedule Interval (Deadline) ▶ Multi-Data Conversion for Partial Change of Master or Transaction Data ▶ Excludes the CATT program
Interface | Simple Lookup Process - Return the list after a simple inquiry - Simple calculation and check process of less than 3 times - Fewer than 4 key table-related processes | Processes without argument variants1) or append items2) - Complex calculation and check processes of less than 3 times - Fewer than 4 key table-related processes - BDC using 1 simple transaction | Complex processes with argument variants or item additions - More than 3 simple calculation and check processes - More than 4 key table-related processes - BDCs that use less than 3 transactions and contain complex screens - The item uses a simple BAPI Function | Complex processes that require additional functionality - More than 3 complex calculation and check processes - Complex BDCs that use 3 or more transactions - The item is complex or uses more than one BAPI function | . Complexity4 or higher If there is a need for consultation | Additional development program for interface with external systems ▶ RFC / BAPI Interface ▶ iDoc Interface ▶ Interfaces through DB Link are categorized into On Line, Report, and Batch. [Definitions] ▶ Argument Transformation: The part that needs to be changed, such as changing the code value of the target system, splitting, consolidation, etc. Transforming Legacy product code and SAP product code by managing mapping table, splitting text arguments with constant format and transforming them into data for use ▶ Add Item: When creating an additional item through a Master or related Table query in addition to the item input as an argument. * Add customer information/price information based on the customer code, copy the details of the billing document from the deficit order to create a deficit order.
Enhancement | Simple process - Use less than 2 simple functions IMG Configuration - Simple code registration | Simple process - Use less than 3 complex functions - Simple calculation logic added IMG Configuration - Settings related to two or more modules | Complex process - Use less than 5 complex functions - Fewer than 4 calculations or logic implementations - Simple on-screen process IMG Configuration - Establishment of new processes | Complex process - More than 5 complex processes - Implement more than 4 calculations or logic - Complex screen process IMG Configuration - Establish two or more impactful processes | . Complexity4 or higher If there is a need for consultation | Adding some functionality to a native SAP R/3 program to suit your needs. Commonly referred to as user-exit ▶ User Exits & Customer Exits ▶ Field / Screen / Function / Menu Exits ▶ Function Module Exits ▶ IMG Configuration
[RPA]
* Scope of quotation: Analysis, design, development, exam, operation transfer -> Analysis design, man-hours of customer communication roles (project leading roles) are further examined
* If the difficulty calculation unit (step) includes multiple work objects/types, it is calculated by adding them up.
category | Work to/type | C0 | C1 | C2 | C3 | C4 | C5
Document processing (Office Appl.) | Excel | . Not used . Exceptions only apply when there is no data manipulation | . Difficulty below C2 | Low amount of extract/processing data Processes only numerical structured data Simple output generation with no file manipulation | Moderate amount of extract/processed data Has processing for unstructured data Manipulating and saving files using common functions Generate files of normal difficulty The complexity of the processing logic is moderate | Extremely large amount of extract/processing data Lots of unstructured text data processing There is file operation using advanced functions High demand for data analysis and visualization .of complex issues such as macro processing Has a background task | . Difficulty above C4
| PPT, Word, PDF | . Not used . Exceptions only apply when there is no data manipulation | Not used | . Difficulty below C3 | 1 document to be processed, low throughput The document is structured It is an open and search-oriented process of documents. Very simple copy and save | More than one document to be processed, high throughput Unstructured content exists (location, form) Normal level editing and storage with search Take action | A large number of documents to be processed, with a very high throughput There are a lot of unstructured documents and contents. (location, form) Complex level editing and storage with search Perform tasks, including forms and graphs, etc.
| Image processing | . Not used . Exceptions only apply when there is no data manipulation | Not used | . Difficulty below C3 | Single processing document, low throughput Simple form, formality of the image and Very accurate | Multiple processing documents, high throughput The formality and accuracy of the form and image Moderate Images do not contain handwritten text | Multiple processing documents, high throughput The formality and accuracy of the form and image Low-level Images include signatures and handwritten
| (common) |  | If there are various forms, it is necessary to precede/parallel the standardization of the forms through PI and change management, which may affect the period and man-hours.
Business System (Biz Appl.) | ERP, WEB, C/S, Solutions | . Not used . Exceptions are made only in the absence of system standing force | . Difficulty below C2 | Simple access with a single screen Consists of a simple query of conditions Simple condition processing, consisting of storage Generate a single, simple output With standardized simple single surface processing No Pop-up | Approaching the target with one or two operations Consists of a query of moderate conditions . There are a few branches according to the case Consists of processing and storage of moderate conditions Single Download, Output Generation A small number of target screens, moderate screen complexity There are a few pop-ups, and the processing is simple . Selector Unrecognizable ObjectNo Requires single grid object processing Presence of some simple non-standard screens | Navigating through complex steps .Consists of multiple and complex condition queries . There are multiple branches depending on the case Complex level of processing, consisting of storage Multiple downloads, output generation Multiple target screens, high screen complexity Multiple pop-ups, complicated processing for each case Multiple Grid Objects need to be processed. There are many non-standard screens. . Selector Unrecognizable Object Processing Required (X-Platform, WebDyn, etc.) | . Difficulty above C4
| Groupware (E-mail, Portal) | . Not used . Exceptions are made only in the absence of system standing force | . Difficulty below C2 | Simple reading and processing of received small number of e-mails The subject and body of incoming emails are standardized Handle a single incoming attachment file Creating outgoing mail is simple, so you can use Copy & Paste Level: Processing a single transmission attachment file | There are a lot of incoming mails, and according to simple conditions, Search, viewing, and processing are required The subject of the incoming email is standardized, and the body is unstructured Becomes Receipt attachment file is plural Compose outgoing e-mails (recipient, subject, body) Relatively simple and formalized Transmission attachment files are plural The screen and formality of the portal are high, Low complexity of processing conditions | If you receive a lot of incoming mail, it will depend on the complicated conditions. There is search, conditional reading and processing The formal level of the incoming mail subject and body is Low, complex searches occur The number and type of incoming attachment files vary widely .Recipient, Subject, Body) The level of complexity is very high and there is logic There are multiple files attached to the transmission, and the case is Needs a choice .It is low in formality with the screen of the portal, High complexity of search and processing conditions | . Difficulty above C4
| External Systems | . Not used | . Difficulty below C2 | A single site with no access restrictions Inquiry/confirmation of simple information, securing No calculation, comparison, or processing of data Structured data processing The site is standardized, and changes are made Very low Chance | There are restrictions on security, permissions, etc. . Requires access to several sites with different URLs Lookup data exists as unstructured data Lookup/Verification data is moderately complex Calculations, comparisons, processing, etc. of some data Has processing No complexity in creating/storing processing results (Amount of information, number of documents/types, conditions, etc.) The site is more or less standardized. Moderate complexity, difficult to navigate Not Site changes occur but are perceptible | There are strong restrictions (security, permissions, control, etc.) when accessing . Accessed multiple sites with different URLs Search/check centered on unstructured data There is a lot of data processing (calculation, comparison, processing, etc.) High complexity Creation/storage of processing results is complicated (Amount of information, number of documents/types, conditions, etc.) The site screen is irregular and unstructured/ It's a complicated process, and navigation is also a complicated process. Tested Changes to the site occur frequently, and a separate Unannounced and uncontrollable | . Difficulty above C4
| (common) |  | If there are various forms, it is necessary to precede/parallel the standardization of the forms through PI and change management, which may affect the period and man-hours. If a process change is accompanied by a change in the legacy system and change management, it may affect the time frame and man-hours. Waiting due to changes in the target system during development, increased exam effort, etc., may affect the duration and man-hours.
Processing Logic /standardization | When calculating the difficulty, Considerations | . Not used | . Difficulty below C2 | The level of standardization/standardization of work is very high, Almost no chance of change It is a complete rule base business . In/Output forms have a very high level of standardization The processing business case is simple and the branch is None or minimal Recognized, unrecognized exception cases are Almost none No or minimal validation of the value Inquiry-oriented and detailed item processing Very low complexity | The level of standardization/standardization of work is high, Be able to recognize and respond to changes Most of the work is Rule Based . The level of standardization of the in/output form is high, Only some require minimal standardization The processing work case is plain, and the number of Branch exists Recognized, unrecognized exception cases are Easily manageable Validation for decimal values Exists Processing complexity of details is moderate | The level of standardization/standardization of work is very low, Change Chance is high. PI, Change Management High need . There are cases where it is not a rule base . The level of standardization of the In/Output form is very low. Standardization and change management required The business case is complex, and the branch is plenty It is difficult to identify the exception case, and when it occurs, Can be difficult to handle Verification of the value is important and there is a risk Very high processing complexity for detailed items | . Difficulty above C4
Additional Considerations Matters (common) | Difficulty Increases | Exceptions (ex, Silverlight) application, etc. If the target system is affected by the instability (speed, error, frequent changes, etc.) of RPA development and operation. . When DB program access and linkage processing are required If there is a large difference between the development environment and the operating environment, and additional exams occur during the operation transfer. If the standardization level of the user's operating environment is low (e.g., the standard is broad and uncontrolled due to the local PC environment) If it is difficult to obtain sufficient exam data, if you rely on separate writing, or if the exam time (condition) is limited. When it is absolutely necessary to ensure the integrity of multiple connected systems. In the event of an unexpected failure, when the recovery (rollback) range is wide and the sharing range is wide. When development is required to reflect modularization in consideration of diffusion/reuse . Number of Queues High security constraints on systems/documents (e.g., encrypted documents, access control, etc.) When it involves some changes to the existing system and requires requirement definition and SM support
| Difficulty Reduction Factors | The target is different, but the same work, the same format is automated processing (ex, subsidiary/site expansion of the same work) . Scripts with little modification and high level of recycling When there is a lot of reuse of existing common modules
[Mobile]
※ Precautions regarding the application of mobile change rate: In the case of mobile native development, it is difficult to calculate the recycling rate by judging whether it is actually recyclable by identifying it simply by identifying it as a function definition of each module due to frequent policy changes in OS and distribution channels (Google Play, Apple AppStore), API level limitations, and fragmented terminal structure. Even when calculations are required as estimates, if they are not clearly identified as recyclable, the recycling rate should be limited or kept to a minimum (maximum of 0.5) if it is not clearly identified.
Processing Type | entry | C1 | C2 | C3 | C4 | C5
App | Hybrid_FrontEnd | - Inquiry: A screen that contains a simple inquiry, a single query condition (a condition that does not check validation) - No more than 3 UI features | - Input: Simple input (less than 6 inputs) - Inquiry: Inquiry screen under 2 search conditions (Validation of search conditions) Screens with fewer than 6 query columns, simple on-screen branching based on conditions, and simple calculation results - No more than 6 UI features | - Input: Complex input/correction screen - Inquiry: A screen that requires specific functions such as sorting by column through 3 or more search conditions or branches Fewer than 10 lookup columns - No more than 9 UI functions | - Input: Complex input/correction screen (including linkage processing through calling other pages to modify input) - Inquiry: A screen with complex functions such as modification, deletion, and movement within the screen after viewing - Development of complex external open source application function (schedule calendar) - No more than 12 UI features - Map function linkage (Google, Naver, KaKao, etc.) screen development | - Hardware control, application of new technologies (WebRTC, WebSocket, Canvas, Service Worker) - Developed 2 or more external open source application functions (Swiper, calendar calendar)
| Native_iOS | - Simple screen processing using a single ViewController + 1 View (Story Board) - Internal asset/resource simple lookup - External URL links and simple lookups | - Simple screen processing using 2~3 ViewControllers (StoryBoard + AutoLayout) - CoreData data management using 1 table - Configure your project environment - Build and package your app - Obfuscation solution linkage - Add Component Native Animation | - Screens with common UI such as StoryBoard Animation, Navigation/Table View/Collection View, and screen composition by coding - 1 server-to-client communication or app-to-app communication event - CoreData management and TableView linkage using multiple tables - Utilize native basic functions provided by OS (Camera, Push, LocalNotification, Alarm, etc.) - Leverage Keychain features - Create and build libraries - 2~3 Layout components, widget screen development, event app launch, and connection - Native Animation linkage between screen/component (when component replacement and animation are implemented in combination) | - 2~3 server-to-client communication or app-to-app communication events - Universal Layout Support / Dynamic Screen Composition / Apple Watch - Map function linkage (Google, Naver, KaKao, etc.) screen development - Background task development - Download and upload files and Share Extension - Separate data processing for security ( Secret/Decryption ) - Development of asynchronous data processing functions - 3rd Party Solution Integration - Object C - Swift Mixed Development - Develop 4 or more widgets for Layout components | - Four or more server-to-client communication or app-to-app communication events - Media storage and playback (iPad PIP development / Bluetooth device linkage / VoIP / accessory linkage) - Branching of business logic and a screen with a lot of exception handling - SiriKit integration - Metal interlocking development - Apple App store app registration and review (Pre-technical review before screening, app distribution and console setting, response to audit results) *Metadata and image resources need to be corresponded to in the UX - When customizing native functions provided by the OS (self-implementation of camera function, gallery multi-selection, etc.) - Develop UI Components or Layouts that are not provided by the OS (Radial UI (Circular, Radial>
| Native_Android | - Simple screen processing with a single Activity or 1 Fragment - Internal asset/DB simple lookup - External URL links and simple lookups | - Simple screen processing using 2~3 fragments - Internal DB data management using 1 table - Build and package your app | - Screens with common UI such as ActionBar, Navigation Drawer, Theme, and Style - 1 server-to-client communication or app-to-app communication event - Internal DB data management using multiple tables - 2~3 Layout components, widget screen development, event app launch, and connection - When using the basic functions of Native provided by the OS (Camera, NFC, Notification, Alarm, etc.) - Add Component Native Animation | - 2~3 server-to-client communication or app-to-app communication events - Tablet Support / Dynamic Screen Configuration - Map function linkage (Google, Naver, KaKao, etc.) screen development - Android Service and Alarm Task Development - Download and upload files - Separate data processing for security ( Secret/Decryption ) - Development of asynchronous data processing functions - Broadcast Receiver Implementation - 3rd Party Solution / NDK Library Integration - Obfuscation solution linkage - Develop 4 or more widgets for Layout components - Widget Background linkage - Native Animation linkage between screen/component (when component replacement and animation are implemented in combination) | - Four or more server-to-client communication or app-to-app communication events - Media storage and playback - Branching of business logic and a screen with a lot of exception handling - Bluetooth interlocking and IR control - Google App store app registration and review (Pre-technical review before screening, app distribution and console setting, response to audit results) *Metadata and image resources need to be corresponded to in the UX - When customizing native functions provided by the OS (self-implementation of camera function, gallery multi-selection, etc.) - Development of UI Components or Layouts that are not provided by the OS (Radial UI (Circular, Radial>
[Based on Big Data-Data Engineering Difficulty]
category | C1 | C2 | C3 | C4 | C5
EDP_Ingestion | Refer to 1~2 data, and if you process simple logic | - Refer to 3~4 tables, and handle simple logic | - Refer to 5~6 tables, and if you are dealing with simple logic | - Refer to more than 7 tables, and handle simple/complex logic | . Complexity4 or higher If there is a need for consultation
|  | - Refer to 1~2 tables, and when processing complex logic | - Refer to 3~4 tables, and handle complex logic | - Refer to 5~6 tables, and handle complex logic
EDP_Enrich | Refer to 1~2 data, and if you process simple logic | - Refer to 3~4 tables, and handle simple logic | - Refer to 5~6 tables, and if you are dealing with simple logic | - Refer to more than 7 tables, and handle simple/complex logic | . Complexity4 or higher If there is a need for consultation
|  | - Refer to 1~2 tables, and when processing complex logic | - Refer to 3~4 tables, and handle complex logic | - Refer to 5~6 tables, and handle complex logic
As for the standard man-hours for use in the field, it is recommended to set standards for each type of construction and proceed in the direction of proceeding.
Due to the recent characteristics of EDP, there are many cases where various new technologies are applied and applied.?This may require new criteria for the program and may require the development of additional items